## Priorities
Areas for priority action | Resonsible Body | Senior Responsible Officer (SRO)
Priority 1 - Strategic Oversight and Governance
Leaders at Halton local authority and the NHS Cheshire and Merseyside ICB should cooperate at pace to improve the shared strategic oversight, governance, support and challenge to drive improvements to meet the needs of children and young people with SEND in Halton. | Halton Borough Council and NHS Cheshire and Merseyside Integrated Care Board (ICB) | Education, Inclusion & Provision (HBC)
Priority 2 - Cohesive communication / joined up systems
Leaders in the local authority, ICB and education, health and social care providers should improve the efficiency and quality of their information gathering and sharing processes to ensure that children’s and young people’s needs are understood accurately and met more swiftly and effectively through coordinated approaches. | Halton Borough Council and NHS Cheshire and Merseyside Integrated Care Board (ICB) | Val Amor - Head of Service, Early Help and Intervention (HBC)
Priority 3 – Joint Commissioning
Leaders across education, health and social care should improve the joint commissioning of services to ensure that children, young people and their families receive sufficient support to have their needs met effectively. | Halton Borough Council and NHS Cheshire and Merseyside Integrated Care Board (ICB) | Kevin Greaves - Head of Service Commissioning (HBC)
Priority 4 – Early identification of need and access
Leaders across education, health and social care should urgently improve the early identification of needs and access to specialist health pathways, including the neurodevelopmental assessment pathway and speech and language therapy and the support available, while children and young people wait. | Halton Borough Council and NHS Cheshire and Merseyside Integrated Care Board (ICB) | Philip Thomas - Associate Director Transformation and Partnerships Halton (ICB)
Priority 5 – Education Health and Care Plans
Leaders across education, health and social care should improve the timeliness of new EHC plans and updates to EHC plans following the annual review process, so that, if appropriate, children and young people receive an effective EHC plan within statutory timescales. | Halton Borough Council and NHS Cheshire and Merseyside Integrated Care Board (ICB) | Charlotte Finch - Head of Service, SEND (HBC)

## RAG Rating
Status | Definition
Grey | Action not started.
Blue | Action completed and signed off,
Green | Action on target.
Amber | Action delayed and likely to miss completion date.
Red | Action significantly delayed and has missed completion date (new completion date required) or, No actions made to progress.

## Priority 1
Priority 1 - Strategic oversight and Governance
Ref | Actions (what we will do) | Owner | Timescale | Success criteria (how we know it's achieved) | Progress (what steps we have taken so far) | Outcome/impact (the difference this made) | Evidence (how we show this) | RAG | Progress since last SSIB | Next steps
1.1 | Establish Halton SEND Improvement Board | Martin West | 2024-03-01 | Board Meetings diarised for 2024/25 | Tracy Ryan diarising Board Meetings. ToRs drafted Membership drafted Governance and Reporting agreed | The Halton SEND Strategic Improvement Board brings together system senior leaders with a shared strategic vision, direction and challenge, are accountable for, oversee and monitor the delivery of the Halton SEND Strategic Plan, SEND Improvement Plan and SEND Local Area inspection Recommendations. | Terms of Reference Governance and Reporting algorithm Membership from all partner organisations Schedule of meeting dates Schedule of Reporting
|  |  | 2024-03-01 | Terms of reference agreed by partners | [5 empty] | TORs to be approved at HSSIB 17/04/2024
|  |  | 2024-03-01 | Membership agreed | [5 empty] | Membership to be agreed at HSSIB 17/04/2024
|  |  | 2024-04-01 | Independent Chair recruited. |  |  |  |  | 23/3/24 Contact made with prospective Independent Chiars for initial discussion. | Discussion meeting diarised.
|  |  | 2024-03-01 | Governance and Reporting mechanisms in place
1.2 | Establish Halton SEND Delivery GroupImprovement Board | Martin West | 2024-03-01 | Delivery Group Meetings diarised for 2024/25 | Tracy Ryan diarising Board Meetings. ToRs drafted Membership drafted Governance and Reporting agreed. | The Halton SEND Delivery Group will provide robust multi agency oversight for the delivery of services across the SEND partnership and the programme of change required to provide an outstanding service to children and young people with Special Educational Needs. The Delivery Group will also have responsibility for the delivery of the recommendations outlined in the Halton local Area partnership SEND Inspection. The Delivery Group will provide key governance ensuring pace, challenge and oversight for all aspects of SEND improvement across the partnership. | Terms of Reference Governance and Reporting algorithm Membership from all partner organisations Schedule of meeting dates Schedule of Reporting |  |  | TORs to go for approval to HSSIB
|  |  | 2024-03-01 | Terms of reference agreed by partners
|  |  | 2024-03-01 | Membership agreed
|  |  | 2024-03-01 | Joint H&SC Chairs recruited.
|  |  | 2024-03-01 | Governance and Reporting mechanisms in place
1.3 | Establish Halton Priority Workstreams | Charlotte Finch and Philip Thomas | 2024-03-01 | Senior Responsible Officers leading 5 Priority Action Plan areas. | SRO's identified for all 5 Priority Areas. Action Plans developed and submitted to ofsted and awaiting feedback. Governance Structure in Place. | Halton SEND Priority Workstreams will ensure the operational delivery of the Halton SEND Strategy and Improvement Plan requirements. The SRO's will be accountable to and report to the Delivery Group and by exception to the Improvement Board on progress, issues and challenges. The Workstream SROs will be accountable for the delivery of their PAP action plan. | Workstream Priority Action Plans Governace and Reporting algorithm Meeting schedule Halton SEND Integrated Performance Dashboard
|  |  | 2024-03-01 | Each PAP has a robust action plan in place with clearly identified leads, timescales, outomce measures and Evidence base. | [5 empty] | All PAP workstreams reporting to Halton SEND Delivery Group on bi-monthly basis
|  |  | 2024-03-01 | All 5 PAP areas have diarised meetings scheduled for 2024/25
|  |  | 2024-03-01 | Clear lines of governance and reporting are in place to Halton SEND Delivery Group and Halton SEND Improvement board.
|  |  | 2024-06-01 | Establish SEND Integrated Performance Dashboard Workstream |  |  |  |  | Halton SEND Integrated Performance Workstream established | Separate reporting line added to PAP 1 for reporting.
1.4 | Establish a SEND Programme Management Office | Charlotte Finch | 2024-05-01 | Recruit a PMO Manager | Agreed joint recruitment of PMO Manager for 2 year fixed term contract. | Halton SEND Partnership will have a fully functioning Programme management Office in Place. | Workforce in place. Full suite of reporting templates/reports. Governance Structure Reporting and Meeting Schedules Integrated perormance Dashboard. |  | 03/04/24 - Draft JD/PS complete and sent for job matching and pay banding awaiting outcome. | Advertise and recruit PMO lead.
|  |  | 2024-05-01 | PMO human resource support and Administration in place. |  |  |  |  | Have interim support identified | Consideration at Delivery Group for administration support is required including financial resource.
|  |  | 2024-04-01 | Shared Central SEND repository of information in place. |  |  |  |  | Sharepoint Folder established as central respository of information. | All leads SROs to ensure that information is forwarded to Tracy Ryan for governance oversight and tracking.
|  |  | 2024-04-01 | Standardised Report format in place |  |  |  |  | All Action Plans reviewed and formatted for consistency and tracking. | Approval of PAP Action Plan tracker at HSSIB 17/04/2024
|  |  | 2024-04-01 | Standardised Highlight Report format in place.
|  |  | 2024-03-01 | Clear governance and Reporting in place |  |  |  |  | Meeting shcedule of Halton SEND Strategic Improvement Board and halton SEND Delivery Group circulated to all members and SROs to ensure reporting submissions achieved.
1.5 | Complete survey of parents/ carers/ families and CYP to appraise all elements of the SEND Area partnership relating to leadership visibility and satisfaction with general SEND Services across the Local Area Partnership | C Finch/ Programme Lead | April 2024 (repeated 6 monthly) | Survey coproduced and published. Baselines established in understanding experiences of leadership working for improved outcomes and satisfaction with general SEND Services across the Local Area Partnership. | One survey already completed as par as part of DBV work. Expand on these to develop new survey to form baseline. SROs generating questions relative to their priority areas to help form the overall survey. Programme Lead has commenced drafting of the survey. | The partnership will possess detailed insight into the experience and views of CYP and their families on the effectiveness of Halton's leadership working and satisfaction with general SEND Services across the Local Area Partnership. | Parents report improved satisfaction with general SEND Services across the Local Area Partnership (Education, Health, Children's Social Care) evidenced via responses from parents/carers and children and young people to SEN satisfaction survey. by December 2024 20% improvement. June 2025 25% improvement. Dec 2025 40% improvement. KPIs across all areas of SEND show at least 25% improvement by sept 2025. (baseline measures to be agreed and established) |  | 27/3/24 email sent to parents/carers, SEND R US CIC, HBC Short Breaks Service for Children with Disabilities, HBC Specialist Teaching & Advisory Service, Inclusive Needs Club (INC), Vibe Project, Youth Provision Activity Club, Halton Speak Out Youth Group, Halton Youth Cabinet, SEND Youth Needs Club (SYNC) and Health CYP/Parents/Carers Panels to evidence co-production of survey. Questions for inclusion in survey received from PAP 1, PAP 2, PAP 3, and PAP 5 to-date. | PAP 4 questions being reviewed and to be submitted by 19/04/2024. Information to be analysed and reported.
| Complete survey of parents/ carers/ families and CYP to appraise all elements of the SEND Area partnership relating to leadership visibility and satisfaction with general SEND Services across the Local Area Partnership | C Finch/ Programme Lead | April 2024 (repeated 6 monthly) | Results of survey shared with all stakeholders via a number of workshops and engagement sessions and published on the Local Offer. Post Survey insight report submitted to Improvement Group. | One survey already completed as par as part of DBV work. Expand on these to develop new survey to form baseline. SROs generating questions relative to their priority areas to help form the overall survey. Programme Lead has commenced drafting of the survey. | The partnership will possess detailed insight into the experience and views of CYP and their families on the effectiveness of Halton's leadership working and satisfaction with general SEND Services across the Local Area Partnership. | Parents report improved satisfaction with general SEND Services across the Local Area Partnership (Education, Health, Children's Social Care) evidenced via responses from parents/carers and children and young people to SEN satisfaction survey. by December 2024 20% improvement. June 2025 25% improvement. Dec 2025 40% improvement. KPIs across all areas of SEND show at least 25% improvement by sept 2025. (baseline measures to be agreed and established) |  |  | Stakeholder Event required and feedback on survey results delivered. Publish results on Local Offer website. Post Survey insight report submitted to HSSIB June 2024.
1.6 | Halton SEND Strategy and action plan reviewed and revised in line with Ofsted Inspection and PAP 2022 - 2025 | Denise Roberts | 2024-03-01 | A refreshed SEND Strategy and accompanying action plan coproduced, agreed and published. | Halton SEND Strategy 2022 - 2025 has been refreshed to include the findings and recommendation of the Halton SEND Local Area inspection | 1) Strategic leaders across the Local Area Partnership work well/collaboratively together to set a consistent direction for SEND improvement. 2) Revised priorities are agreed/determined based on recent inspection outcomes and are known and understood across the partnership. 3) Children, families and stakeholders across Halton are aware of the SEND Strategy, and what the partnership are trying to achieve. 4) That Children, young people and families will benefit from the improvements across all sevices |  |  | 21/03/2024 'Revised Halton SEND Strategy 2021 - 2025. Priority Action Plan and Governance published on Local Offer Website
1.7 | Halton SEND Strategy 2025 - 2028 to be co-produced | Denise Roberts | 2024-05-01 | Halton SEND Strategy Working Group established. |  | Halton SEND Strategy 2025 - 2028 will have been co-produced with CYP, their carers and families. Our approach will be grounded in what works best to improve outcomes for children and young people so that they can have the best future possible and thrive as part of our local community. We will have been efficient and evidneced based in prioritising what we know we need to focus on to provide the right level of support through education, health and care. | Halton SEND Strategy 2024 - 2028 published. Meetings, workshops minutes and agendas. Vocie of CYP, Parents and Carers.
|  |  | 2024-05-01 | Equal partner membership established
|  |  | 2024-05-01 | Joint leadership with Halton Parent and Carers Forum in Place
|  |  | 2024-05-01 | Bi-Monthly workshops diarised to ensure communication, engagement and participation in the development of the strategy.
|  |  | 2024-06-01 | Clerly identified Aims, Objectives and Outcomes identified
|  |  | 2024-06-01 | Integrated SEND Dashboard used to identify priorities and monitor improvements.
|  |  | 2024-11-01 | Draft Strategy coproduced
|  |  | 2024-12-01 | Draft Strategy delivered to Halton Parent and Carer Forum for Approval
|  |  | 2025-02-01 | Draft Strategy delivered to Halton SEND Strategic Improvement Board for Approval
|  |  | 2025-03-01 | Halton SEND Strategy 2025 - 2028 delivered to Halton Health and Wellbeig Board for Apporval and sign off.
|  |  | 2025-03-01 | Halton SEND Strategy 2025 - 2028 published on Local Offer Website
1.8 | Leaders and stakeholders in Halton will ensure there is an Alternative Provision Strategy developed and informed by stakeholders | Charlotte Finch/ L Corlett/ K Greaves | 2024-04-01 | Halton Alternative Provision Strategy and Alternative Provision offer co-produced with all system partners. | AP Strategy in development. First draft complete. Further co-production and financial modelling required. | AP Strategy and model offer will be known by stakeholders. AP offer increases educational options. More CYP will remain in education. Per ex and Fixed suspensions reduced. | Halton Perm ex reduced to be at least in line with regional average- a reduction of 0.03% by July 2025. By Sept 24 Satisfaction survey tells us that 51% of CYP/ families are aware of AP offer in Halton. By June 25 satisfaction survey indicates that 51% of CYP/ families are aware of AP offer in Halton.
AP Strategy submitted to Halton SEND Improvement Board for approval.
AP Strategy submitted to Halton Health and Wellbeing Board for approval and sign off.
AP Strategy published on Halton Local Offer website.
1.9 | Develop a Halton SEND Integrated Performance Dashboard | Michelle Creed | 2024-03-01 | Establish Halton SEND Integrated Performance Dashboard Workstream | Invitations to workstream sent out and first date diarised. | Halton SEND Strategic Improvement Board, Halton SEND Delivery Group and partners will have an evidenced based perfomance dashboard that will identify the quality, effectiveness and experience of services provided to CYP and their families. | Halton SEND Integrated Performance Dashboard |  | Worstream established. Identified Linda Edwards, Louise Owen C&M ICB, Paul Moore and Scott Middlehurst Halton LA, Julia Rosser Public Health HBC as leads for the development of SEND Integrated Performance Dashboard
|  |  | 2024-03-01 | Diarised Meetings in place | Agreed frequency of meetings |  |  |  | All meetings diarised
|  |  | 2024-05-01 | Recruit Halton SEND Data Analyst | Approved Data Analyst post at Halton SEND Delivery Group |  |  |  | Post Agreed and funded. Job Description agreed. | Interviews and recruitment to position.
|  |  | 2024-04-01 | Review national and local indicators and produce long list. |  |  |  |  | Long list drafted 91 indicators identifed. | Circulate to SROs to agree set of indicators to ensure all outcome measures are identifed and agreed.
|  |  | 2024-04-01 | Agree suite of indicators to be used for the Halton Integrated Performance Dashboard with SROs to ensure all priority actions outcomes can be measured. |  |  |  |  | Long list circulated to SRO's for input into the build of the dashboard. | Agree draft dashboard indicators and build dashboard.
|  |  | 2024-05-01 | Draft Halton SEND Integrated Performance Dashboard submitted to SROs for comments and draft approval
|  |  | 2024-05-01 | Halton SEND Integrated Performance Dashboard submitted to Halton Delivery Board for approval
|  |  | 2024-06-01 | Halton SEND Integrated Performance Dashboard submitted to HSSIB for approval
|  |  | 2024-07-01 | Final version SEND Integrated Performance Dashboard completed.

## Priority 2
Priority 2 - Cohesive communication / joined up systems What do we want to achieve? Leaders in the local Authority, ICB and education, health and social care providers will improve the efficiency and quality of their information gathering and sharing processes to ensure that children and young peoples needs are understood accurately and met through a swift coordinated approach
Ref | Actions (what we will do) | Owner | Timescale | Success criteria (how we know it's achieved) | Progress (what steps we have taken so far) | Outcome/impact (the difference this made) | Evidence (how we show this) | RAG | Progress since last meeting - SSIB (SEND Strategic Improvement Board) | Next steps
PAP 2.1 | Complete survey of parents/ carers/ families and CYP to appraise all elements of the SEND Area partnership relating to Communication, Coproduction, Joint Working, the Local Offer and Information Sharing, to gather a performance baseline | C Finch/ Programme Lead | April 2024 (repeated 6 monthly) | - Survey coproduced and published. Baselines established in Co-production, Communication, Information Sharing and the Local Offer. - Results of survey shared with all stakeholders via a number of workshops and engagement sessions and published on the Local Offer. Post Survey insight report submitted to Improvement Group. "We Said, We Did" Outcome report published - so CYP/ Families can see how their input is shaping Service | - One survey already completed as par as part of DBV work. Expand on these to develop new survey to form baseline. SROs generating questions relative to their priority areas to help form the overall survey. Programme Lead has commenced drafting of the survey. | - The partnership will possess detailed insight into the experience and views of CYP and their families on the effectiveness of Halton's Communication, Coproduction, Joint Working, Local Offer and Information sharing. feedback from CYP and Families will be used to guide, influence and shape both strategy and operational practice. - CYP and their families will know that their views are influencing and shaping strategy and operational practice. CYP and their families will have increased confidence that their views are central to strategic design- via the publication of "We said, We did" outcome report. | - Published survey outcomes. Post Survey Insight Report. “You said, We did" Outcome Report. By June 2025, at least 51% of CYP and their families will tell us via survey that their input is sought, and used to guide, shape and influence strategy and operations | On target | - This action is underway. - Questions sent to Emma with help of Tracy Ryan | Awaiting Survey to be agreed and sent out
PAP 2.2 | Relaunch the Coproduction Charter and implement | Mike Stapleton-Chambers School Improvement Officer Tracy Ryan Policy Officer | 2024-07-01 | - Co–production charter/Strategy shared with all parents/carers, children and young people, services and settings, through training, workshops, and focus groups and published on the local offer. - Workshops completed to embed the co-production charter. | - Created a Co-Production Team from a range of stakeholders at all levels who agreed this action plan together. - Soft launch of co-production charter completed in November 2022. | - Children, young people and their families are confident that their voices are heard and drive change at the most fundamental and strategic levels. - Full and effective use is made of digital systems and children, young people and their families are empowered to take ownership of their needs as a result. | - By Jan 2025 50% of parents/ carers/ CYP report that they feel involved and listened to (via survey). - By August 2025 65% of of parents/ carers/ CYP report that they feel involved and listened to (via survey). - By January 2026 75% of of parents/ carers/ CYP report that they feel involved and listened to (via survey). | On target | Owner of action agreed. Looking at luanch to be at the Family Hub Conference in July 24 | Adam Hindhaugh to discuss with Ideas Alliance regarding the conference then meet with Tracy Lynch to finalise
PAP 2.3 | Coproduce the 'Tell it once' framework for children and young people with SEND with all stakeholders to identify potential options for positive change. | Rhona Hobson- Principal EP | Sept 2024 | - Revised "Tell it Once" Framework signed off by the Delivery Group. - Revised "Tell it Once" Framework communicated effectively to all partners and stakeholders through a series of engagement events and piublished on the Local Offer. | - Family Hubs have undertaken a Proof of Concept with a digital provider to implement a complete Digital Solution from 0-19 (25). - Final sign off and approval to be presented at Executive Board on 22nd February. - Final build should last 3-4 months. | - Revised "Tell it Once" approach is embedded in both culture and practice accross the Halton Partnership. - Parents and carers report that they do not have to repeatly re-tell their story to professionals. - Greater efficiency seen in CYP/ family access to services. | - Parents and carers report that they do not have to repeat their story to professionals. Greater efficiency seen in CYP/ family access to services. - By September 2024 51% of CYP/ Families surveyed, report that access to services is efficient. - By June 2025, 75% of CYP/ families surveyed report that access to services was efficient. - Reduction in request for Statutory assessment in EY/ KS1. Current % xx. Reduced to (by 2%) by December 2025 - Baseline relating to waiting times required. | On target | Dr Rhona Hobson has arranged a meeting with Charlotte Finch to discuss what needs to be done | Dr Rhona Hobson and Charlotte Finch to meet
PAP 2.4 | Develop, consult, and sign off an information governance protocol across all health and social care partners to support the “Tell it once” culture. | Scott Middlehurst | 2024-07-01 | - Information Governance Protocol signed off by Delivery Group. Information Governance Protocol in use by all key partner agencies | - Workstream lead identified, Scott Middlehurst | - Services share essential information quickly and safely. - Greater efficiency seen in CYP/ Family access to services. - Needs are identified sooner and CYP benefit from earlier intervention. | - By September 2024 51% of CYP/ Families surveyed, report that access to services is efficient. - By June 2025, 75% of CYP/ families surveyed report that access to services was efficient. - Baseline relating to waiting times required. - Reduction in request for Statutory assessment in EY/ KS1. - Current % xx. Reduced to (by 2%) by December 2025 | On target | Scott Middlehurst has agreed to undertake this action and is now starting the scoping work. | Scott to report back his finding a ready for a proposal
PAP 2.5 | Complete a multi-agency joined up review of current ICT systems and processes understanding current ICT platforms used for information storing and sharing and how they interlink. | Scott Middlehurst | 2024-12-01 | - Review complete. - Review findings reported to delivery group. - ICT Systems Forward Plan produced and signed off by Delivery Group. | - Workstream lead identified | - ICT systems potentially improved. - Greater efficiency seen in CYP/ Family access to services. - Needs identified sooner and CYP nenefit from earlier intervention. | - By September 2024 51% of CYP/ Families surveyed, report that access to services is efficient. - By June 2025, 75% of CYP/ families surveyed report that access to services was efficient. - Baseline relating to waiting times required. Reduction in request for Statutory assessment in EY/ KS1. - Current % xx. Reduced to (by 2%) by December 2025 | On target | After a meeting with Daniel Spooner and Scott Middlehurst it was agreed Scott wasn't the best to lead of this. | Scott Middlehurst will look for his equivalent in the NHS. Emma Power to speak to the Transformation Team to see if they are covering any of this work and if they might help
PAP 2.6 | Identification and scoping of longer term SEND IT needs utilising transformative and innovative technology solutions to drive engagement, performance, coordination and improvement across the local area system- October 2024 | Scott Middlehurst | 2024-10-01 | - Scoping Complete, findings reported to Improvement Board with recommendations for a SEND ICT Systems Forward Plan. | - Workstream lead identified | - ICT systems potentially improved. - Greater efficiency seen in CYP/ Family access to services. - Needs identified sooner and CYP nenefit from earlier intervention. | - By September 2024 51% of CYP/ Families surveyed, report that access to services is efficient. - By June 2025, 75% of CYP/ families surveyed report that access to services was efficient. - Baseline relating to waiting times required. Reduction in request for Statutory assessment in EY/ KS1. - Current % xx. Reduced to (by 2%) by December 2025 | On target | Officer agreed and plan going forward agreed. Possible adding Charlotte Finch to this action | Charlotte Finch to meet with Scott to give him a brief of her requirements. Scott will then work to that
PAP 2.7 | Establish and embed Information/Data sharing protocols and systems | Sarah Brennan – Chief Operating Officer Bridgewater NHS Caroline Coyne Chief Executive Officer (CEO) Communicate Sharon English SENDIASS Adam Hindhaugh CMgr Early Help Transformation Lead Heads of Service Areas School Reps | 2024-11-01 | - Scoping and costing of "one door access" completed.Information/ Data Sharing Protocol Report signed off by Improvement Board and Published | - February 2024 - The Family Hub Programme has implemented a signed Joint Controller Agreement between the Local Authority and Bridgewater Community Healthcare Foundation Trust (ICO ref Z2436346);To ensure the best possible support is given to vulnerable children and their families. | - Sevices will report information sharing is effective ensuring that children young people and their families recievve the right support at the right time and have effective robust support and/or plans in place. - Provides a comprehensive understanding of a vulnerable child's needs by integrating health and family-related information. • Promotes early identification of potential health or family-related issues, allowing for timely intervention and preventive measures that ultimately helps avoid crisis situations by addressing concerns before they escalate. • Enhances efficiency in service delivery by minimising duplication of efforts and resources and importantly reduce the burden on families by streamlining access to necessary services through a collaborative approach. • Ensures professionals have a more complete picture, enabling them to make informed and tailored decisions that better serve the child's well-being. • Reduces the risk of overlooking critical information that could impact decisions. • Enhances communication and collaboration between health and family support professionals. • Encourages a team-based approach where professionals from different domains work together for the benefit of the child. | - By September 2024 51% of CYP/ Families surveyed, report that access to services is efficient. - By June 2025, 75% of CYP/ families surveyed report that access to services was efficient. - Baseline relating to waiting times required. Reduction in request for Statutory assessment in EY/ KS1. - Current % xx. Reduced to (by 2%) by December 2025 | On target | It was suggested it might sit with Halton Transformation Unit or a team from the NHS. Due to holidays no contact made | Mike Stapleton-Chambers to speak on Sarah Brennan return from holiday - email has already been sent to request a meeting
PAP 2.8 | Implement a joined up process for an early notification tracker to be held across LA and Health that feeds into the Graduated approach. | Stacey Holleran | 2024-09-01 | - Tracker is fully developed and implemented. - Data monitored for late identificatation | - Working Group Lead Identified | - A robust Early Notification process, CYP with SEND will be identified earlier, have the correct support prior to starting in education. | - A robust Early Notification process, CYP with SEND will be identified earlier, have the correct support prior to starting in education. | On target | Meeting held. Stacey was unsure about this work ans was going to seek guidence from Charlotte Finch | Stacey Holleran to make contact with Charlotte Finch and then report back ways forward.
PAP 2.9 | Review the effectiveness of the local offer and relaunch | Tracy Ryan Policy Officer Michelle Osborne Marketing Communications Manager | 2024-06-24 | - Baseline established by measuring Footfall/ usage for the month of March 2024. - Monthly Local Offer usage reporting process agreed and published (so that footfall is reported to Improvement Group Monthly) Local Offer Engagement Plan complete and approved by Improvement Board. - Survey coproduced and published including sections on the Local Offer. Baselines established to measure improved use and approval of the Local Offer. - Results of survey shared with all stakeholders via a number of workshops and engagement sessions. - Post Survey insight report (including section on the Local Offer) submitted to Improvement Group "You said, We Did" Outcome Report (relating to Local Offer) Published. | - Local Offer Report. - Survey Questions on the Local Offer collated. | - Inceased footfall through/ use of the Local Offer. - Children young people and families with SEND are confident in accessing all information, resources and activites displayed through the Local Offer. . | - Monthly Usage (footfall) on the Local Offer will increase by 51% from baseline by December 2025. - By June 2025 51% of CYP Family Surveyed will tell us they know what the local offer is and find it useful. - Published survey outcomes relating to Local Offer. Published post-- rvey Insight Report. Published "You said, We did" Outcome Report. | On target | Meeting held | Tracy Lynch has gone away to think about the best approach to this and will report back at stakeholders meeting after Easter period
PAP 2.10 | Collect and collate user feedback and share “We said, we did” approach | Tracy Ryan Policy Officer Schools Rep Lindy Webb Headteacher - The Brow Adam Hindhaugh Early Help Transformation Lead | 2025-04-01 | Post Survey insight report submitted to Improvement Group. "We Said, We Did" Outcome report published allowing CYP/ Families can see how their input is shaping Service |  | CYP and their families will know how their views are influencing and shaping strategy and operational practice. CYP and their families will have incfreased confidence that their views are central to strategic design- via the publication of "We said, We did" outcome report. | Published survey outcomes. Post Survey Insight Report."We said, We did" Outcome Report. By June 2025, at least 51% of CYP and their families will tell us via survey that their input is sought, and used to guide, shape and influence strategy and operations. | On target | Brief meetings and emails shared. Mike Stapleton-Chambers also atteneded with Tracy Lynch and Emma Power the Family Hub Digital solution meeting | Tracey will report back on her ideas of best ways forward on this action. Adam Hindhaugh is looking at how it find in with the Family Digital Hub. Possible meeting with OMS about linking Local Offer to Family Digital Hub (cost approximately £20k per year) - Question for prioirty group: Do we want this scoping due to the cost?
| Changes to interactions with parents, carers and young people are published on the Local Offer through a ‘We said – We responded’ section and there is a ‘feedback loop’ so all are aware of issues and families will have increased confidence that their views are central to strategic design- via the publication of "We said, We did" outcome report. |  | 2025-04-01 | Post Survey insight report submitted to Improvement Group. "We Said, We Did" Outcome report published allowing CYP/ Families can see how their input is shaping Service |  | CYP and their families will know how their views are influencing and shaping strategy and operational practice. CYP and their families will have incfreased confidence that their views are central to strategic design- via the publication of "We said, We did" outcome report. | Published survey outcomes. Post Survey Insight Report."We said, We did" Outcome Report. By June 2025, at least 51% of CYP and their families will tell us via survey that their input is sought, and used to guide, shape and influence strategy and operations. | On target

## Priority 3
Priority 3 - Joint Commissioning
Ref | Actions (what we will do) | Owner | Timescale | Success criteria (how we know it's achieved) | Progress (what steps we have taken so far) | Outcome/impact (the difference this made) | Evidence (how we show this) | RAG | Progress since last meeting - SSIB (SEND Strategic Improvement Board) | Next steps
PAP 3.1 | CYP and Family Voice: Complete survey of parents/ carers/ families and CYP to appraise access to effective services (including Therapy Services), resources, assessment and settings. | C Finch/ Programme Lead | April 2024 (repeated 6 monthly) | Survey coproduced and published. Baselines established in access to effective services (including Therapy Services), resources, assessment and settings. | One survey already completed as par as part of DBV work. Expand on these to develop new survey to form baseline. SROs generating questions relative to their priority areas to help form the overall survey. Programme Lead has commenced drafting of the survey. | The partnership will possess detailed insight into the experience and views of CYP and their families on access services across the borough. Parents/CYP know they are listened to and are contributing to improvement activity | - Baseline established via first survey by June 2024, in relation to access to effective services (including Therapy Services), resources, assessment and settings. - By June 25, 20% improvement from initial baseline reported in the experience of effective services (including Therapy Services), resources, assessment and settings. - By December 2025 a further 20% improvement reported in the experience of effective services (including Therapy Services), resources, assessment and settings. - By January 2026, the wider satisfaction survey shows that 51% of CYP and their families feel services are effective across Halton. |  | Owner of action agreed. Looking at luanch to be at the Family Hub Conference in July 24 | Adam Hindhaugh to discuss with Ideas Alliance regarding the conference then meet with Tracy Lynch to finalise
PAP 3.2 | We will review, refresh and relaunch our multi-stakeholder forum that drives a strategic commissioning approach. | Kevin Greaves | 2024-06-01 | Relevant stakeholders identified to ensure multi-stakeholder attendance Refreshed membership in place with revised ToR and governance agreed. | Initial discussion has taken place with relevant stakeholders regarding the purpose and priorities of the forum to ensure alignment with wider strategic direction. There has been a meeting of the Joint Commissioning Board that has discussed the early draft of this plan and comments have been collated on both this and the task and finish group that will be formulated to deliver this work programme. | We will have improved commissioning arrangements for children and young people with SEND across Halton. We will have a strategic, joint commissioning approach to improve the sourcing and monitoring of placements and the connectivity between commissioning, the provider and all stakeholders to ensure outcomes are positive for children and young people. | - 90% attendance at forum meetings. - Parents/ carers representation in the task and finish group that will provide positive feedback following consultation. |  | Discussion taking place via task and finish group as to establishment of forum and whether to utilise existing partnership. | Initial T&F group being arranged by Claire Gurney
PAP 3.3 | We will review our Joint Commissioning resource across the LA & ICB to ensure sufficient support is available to deliver on this plan. | Philip Thomas Zoe Fearon | 2024-09-01 | There is confidence amongst stakeholders that the plan is being delivered with a visible and dedicated presence across the Halton system at a senior level. | Discussion is being planned between stakeholders to develop this initiative further. | We will have sufficient resource to drive the joint commissioning agenda with senior level representation at all key decision making fora across the Halton system. | - Baseline established via first survey by June 2024, in relation to access to effective services (including Therapy Services), resources, assessment and settings. - By June 25, 20% improvement from initial baseline reported in the experience of effective services (including Therapy Services), resources, assessment and settings. |  | Permanent Head of Commissioning Role advertised w/c 22nd April. | Commissioning Redesign Session taking place on 23rd April.
PAP 3.4 | We will review and redefine the joint commissioning strategy co-producing priorities to ensure there are robust arrangements in place to meet children and young people with SEND needs across the system | Kevin Greaves/ Philip Thomas | 2024-10-01 | Implementation of a Joint Commissioning Strategy agreed and understood by providers and families which will provide an understanding of why services have been commissioned, based on evidence. Jointly Commissioned Services will operate more effectively to meet the needs of children and young people at Halton. | The arrangements for joint commissioning have been updated to reflect changes in organisational leadership with the opportunity taken to review partners respective roles and responsibilities. | We will have improved services for children and young people with SEND across Halton. | - Baseline established via first survey by June 2024, in relation to access to effective services (including Therapy Services), resources, assessment and settings. - By June 25, 20% improvement from initial baseline reported in the experience of effective services (including Therapy Services), resources, assessment and settings. - By December 2025 a further 20% improvement reported in the experience of effective services (including Therapy Services), resources, assessment and settings. - By January 2026, the wider satisfaction survey shows that 51% of CYP and their families feel services are effective across Halton. |  | Draft in place and being reviewed | Exploring options to utilise apprentice resource
PAP 3.5 | Review and strengthen commissioning arrangements with academy, maintained and independent and alternative educational providers. | Kevin Greaves/ Charlotte Finch | 2024-12-01 | Commissioning activities will be designed to correctly address identified need to secure improved outcomes for children and young people with SEND at Halton. | Initial discussion has taken place with relevant stakeholders regarding the purpose and priorities of the forum to ensure alignment with wider strategic direction. | Increase in locally commissioned placements and provision. | Baseline established via first survey by June 2024, in relation to access to effective services (including Therapy Services), resources, assessment and settings. |  | Draft AP stratgey being developed. | Stakeholder session planned for late April
PAP 3.6 | Through an effective panel process we will identify current high cost out of borough placements and through sufficiency planning, work with local providers to provide a quality, needs led SEND service closer to home. This will ensure access to service provision that is local, responsive and timely to meeting the needs of children and young people with SEND | Kevin Greaves | 2024-12-01 | Commissioning activities will be designed to correctly address identified need to secure improved outcomes for children and young people with SEND at Halton. | Individual meetings are being planned with providers to review cases in terms of quality and cost. | Improvements in quality of placements and value for money. | - Baseline established via first survey by June 2024, in relation to access to effective services (including Therapy Services), resources, assessment and settings. - By June 25, 20% improvement from initial baseline reported in the experience of effective services (including Therapy Services), resources, assessment and settings. - By December 2025 a further 20% improvement reported in the experience of effective services (including Therapy Services), resources, assessment and settings. - By January 2026, the wider satisfaction survey shows that 51% of CYP and their families feel services are effective across Halton. |  | Current Panel process being reviewed to ensure alignment against need and to provide basis for reconfiguration. | Stakeholder session planned for late April
PAP 3.7 | We will explore options to enter into contract with a local specialist equipment provider. This provider would provide a central equipment hub that would ensure that the correct equipment can be utilised in a needs led way across the borough ensuring children can access equipment at the right time. The contract also includes maintenance, keeping equipment working for longer, ensuring the LA are working towards their Greener Future agenda. | Kevin Greaves/ Claire Gurney | 2024-07-01 | Commissioning activities will be designed to correctly address identified need to secure improved outcomes for children and young people with SEND at Halton. | Focused work has taken place with a local provider to explore possibility of commissioning a stand alone equipment service provider to provide, store, deliver and service specialist equipment. | Single storage facility in place that maintains and distributes specialist equipment that demonstrates quality and value for money. | - Average waiting time for specialist equipment to be reduced to 8 weeks by December 2024. - 100% of usable equipment remains safe and in circulation via maintenance. |  | Proposal was initially discussed at Leadership meeting, but further financial analysis was identified to support the costs of the contract and how funding could be arranged through the DSG. Meeting arranged with finance partner on 18/04/2024 for further discussion. Proposal will then be taken back to leadership for discussion. | Action 1) Meeting with finance partners to discuss contract funding- 18/04/24 Further presentation at leadership team late April.
PAP 3.8 | We will develop a Quality and performance management framework: further development of a shared SEND performance framework across education, health and social care. This will be used across a range of services to monitor the effectiveness of: - The local area in SEND identification and assessment processes; - Outcomes; - Feedback from children, young people, their families and professionals; - SEND commissioning; - Workforce plan. | Kevin Greaves/ Claire Gurney | 2025-03-31 | This information will inform and support the SEND Strategic Partnership to ensure that future services are responsive to local need at a service and system levelled will review process improvement and additional capacity across the service to exploit any further opportunities to improve working practices. | This initiative is a key element of the existing strategy addendum which is being revised in line with the strategy refresh explained in 3.3 above. This will be delivered as part of the Joint Commissioning board and monitored via the SEND Strategic Partnership Forum. | We will have improved performance monitoring of system processes across partners to allow us to accurately identify gaps and key areas of need. | - Baseline established via first survey by June 2024, in relation to access to effective services (including Therapy Services), resources, assessment and settings. - By June 25, 20% improvement from initial baseline reported in the experience of effective services (including Therapy Services), resources, assessment and settings. - By December 2025 a further 20% improvement reported in the experience of effective services (including Therapy Services), resources, assessment and settings. - By January 2026, the wider satisfaction survey shows that 51% of CYP and their families feel services are effective across Halton. |  | Information collated from existing documents to inform new model. | Draft to be produced by end of June

## Priority 4
Priority 4 - Early identification of need and access to specialist health pathways and support whilst waiting
Ref | Actions (what we will do) | Owner | Timescale | Success criteria (how we know it's achieved) | Progress (what steps we have taken so far) | Outcome/impact (the difference this made) | Evidence (how we show this) | RAG | Progress since last meeting - SSIB (SEND Strategic Improvement Board) | Next steps
PAP 4.1 | DCO role Maternity Leave. Liaise with C&M ICB to ensure adequate cover arrangements in place. | Denise Roberts | June 2024 | - Continuity and sustainability of DCO function. - Quality assurance of health advice. - Health representation at multi-agency decision to assess panel. | 13/02/24 Discussions commenced with C&M ICB DCO | Sustainable DCO cover in C&M ICB Halton Place. | - Maintenance of 100% Quality Assured Health Advice signed off by ICB |  | DCO mat leave started early. Interviews held. Offer process underway | Complete offer process and negotiate start date
PAP 4.2 | Using Thrive as a model: | Val Armor to identify |  | Improved, clearly defined, offer across ages and stages and continuum of need. Improved understanding of that offer/ the graduated response to meeting needs - CYP, parents / carers and professionals. Plan in place to address any identified gaps in the existing offer with clear timescales for delivery. | 23/02/24 - Initial workshop held on 21 Feb 2024 | - 'There is more join up offer across the system for key services leading to children and young people having better access to the support they need. - Reduced activity, waiting lists and waiting times in specialist health services - increased activity at universal/targeted level | - CYP and parents / carers report improved access to and experience of early help support - measure tbc - CYP and parents / carers report improvements in their needs being identified and met - measure tbc - Improved access to specialist health services (waiting times and waiting lists). See 4.3, 4.4, 4.5 and 4.6 for further details
| - Scope out existing provision including alignment with education and early help specialist provision and support whilst waiting |  | 2024-07-01
| - Identify gaps in provision across ages and stages |  | 2024-09-01
| - Develop and agree improvement plan |  | 2024-11-01
| - Implement improvement plan - adopting a graduated / Thrive approach based upon meeting need |  | 2025-01-01
PAP 4.3 | Neurodiversity Assessment Pathway: | Karen Hampson |  | - Pathway performance and issues affected it are clearly understood - Resourced action plan developed and agreed - Actions completed and new model implemented - Regular performance monitoring and reporting established and part of SEND oversight arrangements | - Draft performance dashboard developed - further refinement required - Pathway improvement workshop being organised to identify improvement opportunities co-produced with Halton Parent and Carers Forum | Improved access, reduced waiting lists and waiting times, improved experience for CYP and parents / carers | Number of children on waiting list: - Baseline - ADHD 230. Autism 848 (Feb 24) - Targets - ADHD 180 (Mar 25). Autism 700 (Mar 25) - N.B. performance likely to deteriorate before improving Time taken to complete assessment (longest waits): - Baseline ADHD 53 weeks. Autism 107 weeks (Feb 24) - Targets ADHD 40 weeks (Mar 25). Autism 78 weeks (Mar 25) - N.B. performance likely to deteriorate before improving Improved access to specialist health services (waiting times and waiting lists). See 4.4, 4.5 and 4.6 for further details - System working experience measures - tbc - Person reported experience measures - tbc
| - Review waiting list and waiting time data |  | 2024-05-01 | [5 empty] | Baseline performance established
| - Assess demand: historical, current and anticipated future |  | 2024-05-01 | [5 empty] | Historical and current demand information received.
| - Review referral activity - quality, appropriateness and improvement opportunities - xref PAP 4.3 |  | 2024-05-01 | [5 empty] | Workshop planning underway. Awaiting delegate lists from key partner | Planning session w/c 8 Apr 2024
| - Review staffing levels and skill mix |  | 2024-05-01
| - Review system and processes for improvement opportunities |  | 2024-06-01
| - Develop new delivery model, inc staff, systems and processes |  | 2024-08-01
| - Implement future staffing model |  | 2024-12-01
| - Implement process improvements across all affected stakeholders |  | 2024-12-01
| - Monitor improvement (waits, experience, system impacts etc) - with oversight from Halton SEND Executive Group |  | 2025-04-01
| - Introduce active waiting list management and communication |  | 2024-10-01
PAP 4.4 | Speech and Language Therapy: | Kevin Greaves |  | - Service performance and issues affecting it are clearly understood - Clear communications plans developed and implemented across full range of stakeholders - Any requirement to commission additional capacity (ongoing or short-term WLI) understood and actioned - Actions completed and new model implemented - Regular remedial action plan and service performance monitoring and reporting established and part of SEND oversight arrangements | - Weekly meetings between provider and commissioner in place - Remedial action plan received from provider - Capacity and demand modelling commenced - Initial further communications actions underway - Partner meetings (schools, setting, other health providers) underway to build relationships | - CYP will be able to access SALT services in a timely way - Improved partner understanding of service position - LAP will have greater visibility of issues and assurance that appropriate actions are taking place | Number of children on waiting list, waiting times (longest waits, ave wait) Improvements in performance against contract KPIs, e.g.: - response times (initial assessment (75% within 4 weeks of referral received) and treatment commenced (90% within 12 weeks)) - quality improvements (via feedback surveys) - improved appointment attendance / reduced DNAs - outcome measures reflecting the impact of speech and language therapy New provider, baselines to be established from 1st quarter performance report - System working experience measures - tbc
| - Capacity and demand > review to establish sufficiency of ongoing provision > renegotiate the contract as may be required |  | 2024-03-01 | [5 empty] | NDP demand and capacity modelled. Other areas of service provision outstanding.
| - Implement a waiting list initiative for CYP on NDP awaiting SALT assessment |  | 2024-06-01 | [5 empty] | Capacity and demand modelling undertaken. NDP assessment backlog identified and resource requirement identified . WLI SBAR agreed by ICB SLT 21 - resource and catch up trajectory. | Meet with B'Water and Communicate to commence implementation
| - Agree and monitor service wide remedial action plan - with oversight from Halton SEND Executive Group |  | 2024-04-01 | [5 empty] | Remedial action plan in place - actively monitored and managed | Report to SEND Improvement Board
| - Implement further communications and engagement programme: > CYP and parent / carers > System partners |  | 2024-04-01 | [5 empty] | Communications / stakeholder management plan developed and implementation underway | Ongoing implementation in line with plan
| - Monitor and manage service performance and address performance variation as required - with oversight from Halton SEND Executive Group |  | Apr-Dec 24 onwards | [5 empty] | Plan in place to refine KPIs / measures and reporting schedule | Agree reporting schedule. First period reporting
| - Introduce active waiting list management and communication |  | 2024-05-01
PAP 4.5 | Community paediatrics | Karen Hampson |  | - Service performance and issues affecting it are clearly understood - Resourced action plan developed and agreed - Actions completed and new model implemented - Regular performance monitoring and reporting established and part of SEND oversight arrangements N.B. significant interdependencies with 4.3 | - Draft performance dashboard developed - further refinement required - NDP pathway improvement workshop being organised to identify improvement opportunities - Business case sought from provider for advanced practitioner to change skill mix and release paediatricians to increasingly focus on specialist tasks - Provider workshop scheduled for 29 Feb 24 | Improved access, reduced waiting lists and waiting times, improved experience for CYP and parents / carers | - Number of children on waiting list. Baseline - 789 (Nov 23). Target: 600 (Mar 25) - Time taken to complete assessment: - Longest wait. Baseline - 59 weeks (Nov 23). Target: 45 (Mar 25) - % over 18 weeks. Baseline - 62.99% (Nov 23). Target: 50% (Mar 25) - Person reported experience measures - tbc
| - Conduct waiting list cleanse to reduce wasted appointment slots. |  | 2024-06-01
| - Education, training and awareness sessions with partners and stakeholders to support knowledge and understanding of services resulting in a reduction in inappropriate referrals. |  | 2024-09-01
| - Review triage outcome letter to identify advice and signposting to be included. |  | 2024-05-01
| - Review transition between children's and adults’ services and, where gaps are identified, include recommendations, to be approved at Halton SEND Improvement Board, to address these. |  | 2024-08-01
| - Scope the differentiated models of assessment to enable less complex presentations to be assessed by the wider children and young people’s workforce. |  | 2024-10-01
| - Improve capacity within the service to recover long wait times. |  | 2024-09-01 | [5 empty] | Business case received, reviewed and further impact / trajectory information requested and received. Further analysis required | Discuss trajectories with provider to better understand activity and impact of existing and additional resource on waiting times / lists
| - Review opportunity to introduce Patient Initiated Follow Up for service. Report to be considered by Commissioner and Provider for decision |  | 2024-09-01
PAP 4.6 | Other specialist health services: | Karen Hampson |  | - Service performance and issues affecting it are clearly understood - Resourced action plan developed and agreed - Actions completed and new model implemented - Regular performance monitoring and reporting established and part of SEND oversight arrangements | - Draft performance dashboard developed - further refinement required | Improved access, reduced waiting lists and waiting times, improved experience for CYP and parents / carers | - Number of children on waiting list - Waiting times (longest waits, ave wait) - Services, measures, baselines and targets tbc relevant to identified performance issues - Person reported experience measures - tbc - System working experience measures - tbc
| - Review waiting list and waiting time data |  | 2024-05-01
| - Identify performance issues |  | 2024-05-01
| - Analyse causes |  | 2024-06-01
| - Identify and agree solutions |  | 2024-07-01
| - Implement |  | 2024-09-01
| - Monitor improvement |  | Oct 24 onwards
PAP 4.7 | Local Offer: | Tracy Ryan |  | - Published information reflects the services that families should expect to receive. Auditing content provides assurance that it meets specified requirements and is up to date. - Feedback leads to developments of the site and is a measure of quality assurance |  | - There is more join up offer across the system for key services leading to children and young people having better access to the support they need. - Reduced activity, waiting lists and waiting times in specialist health services - CYP receiving the most appropriate support to meet their needs in a timely manner through a graduated, needs based model | - CYP and parents / carers report improved access to and experience of available support - measure tbc - Improved access to specialist health services (waiting times and waiting lists). See 4.3, 4.4, 4.5 and 4.6 for further details
| - Undertake a refresh to incorporate changes from PAP 4.2, adopting an ages and stages x continuum of need approach to support ease of access to support across education, social care and health |  | xref Local Offer review in PAP 2
| - Relaunch, supported by comprehensive communications plan across all stakeholders |  | xref Local Offer review in PAP 2
PAP 4.8 | Develop practitioner learning and development programme (inc core and role specific mandatory training) to improve : - Awareness, understanding and identification of CYP with SEND - Awareness and understanding of specialist health services, their referral / acceptance criteria - The quality and appropriateness of referrals to services - Awareness and understanding of universal and targeted services - Support to CYP / parents / carers, including onward referral / referral to right service | DCO | Oct 2024 | Improved offer across ages and stages and continuum of need. Improved understanding of that offer - CYP, parents / carers and professionals. Reduction in inappropriate and poor quality referrals | - Monthly ICB training model for all health practitioners, new starters or those who want a refresher, objective is to inform about SEND, DCO role and practitioner responsibility. - DCO delivering bespoke training to health providers - Multi-agency /multi-professional training to improve skill and knowledge with health services with partner agencies. | - There is more join up offer across the system for key services leading to children and young people having better access to the support they need. - better use of specialist health services, reduced activity, waiting lists and waiting times - CYP receiving the most appropriate support to meet their needs in a timely manner through a graduated, needs based model | - Training uptake rates across all relevant roles - CYP, parents / carers report improved access to and experience of early help support - Improved access to specialist health services (waiting times and waiting lists). See 4.3, 4.4, 4.5 and 4.6 for further details - Pre and post training evaluations |  | A number of 7 minute Briefings have been drafted - What is SEND? - Working with CYP with SEND - What is an Education, health and Care plan? | Once DCO in post commence development of learning and development programme to improve - Awareness, understanding and identification of CYP with SEND
| Implement |  | Nov 2024 onwards
PAP 4.9 | Family Hubs - optimise the opportunity they present for: | Adam Hindhaugh |  | Forward plan of actions and activities developed and implemented as part of Family Hub development programme | - Solihull Online Parenting Modules available for parents to access including 'Understanding your child with additional needs' - Meeting scheduled for March to discuss Early Years Access into Family Hubs for children with SEND - Digital Solution approved and procured - go live date scheduled for July 2024 | - Families report increased levels of confidence, knowledge and understanding through accessing parenting programmes on how to understand their child with additional needs - Families report being more supported by other parents. - Families report feeling more supported on the pathway whilst awaiting specialist information and advice | - Responses from feedback gained at the end of each parenting programme - measure and baseline tbc - Surveys and feedback gathered through the digital solution - measure and baseline tbc
| - proactive, planned and opportunistic provision of information, advice and support |  | 2025-03-01
| - integrating services / offer |  | 2025-03-01
| - promotion, organisation, hosting and signposting / referring to support, drop-in sessions, events and activities |  | 2025-03-01
PAP 4.10 | Education Graduated Approach - communicate across stakeholders recently mapped offer, incorporating in other communications, information and education programmes as appropriate N.B. wider graduated approach elsewhere in plan - e.g. PAP4.2 | Rhona Hobson | 2024-06-01 | Specific element of the communication and education activities in 4.12 and 4.8 | Education Graduated Approach already mapped. | Increased awareness across all stakeholders of the range of education support available to meet need - including the support available to partners to the educational settings. | As evidenced in PAP 4.12 and 4.8
PAP 4.11 | Communication: Develop and implement communications and engagement activities for CYP, parents / carers and practitioners, including: range of services, where to obtain advice and support, available training and development, promotion of the Family Hubs, Healthy Child Programme, Child Development Centre, Local Offer etc (part of PAP 2) | Mike Stapleton-Chambers | Dates to align to key actions / activities in rest of PAP 4 and PAP 2 | Communication plan aligned to wider PAP 4 improvements successfully developed and delivered, with positive feedback from all relevant audiences | Communication added to PAP 2 to ensure appropriate focus across the improvement programme | Improved level of understanding of local offer, increased utilisation, more appropriate use of available services to meet need, learning and development uptake across practitioners and parents / carers. Priority four outcomes will be cross referenced and aligned with Priority 2. | As a supporting action evidence will be demonstrated through other PAP 4 actions. |  | Mike Stapleon-Chambers has set-up a briefing with schools and setting to launch the SEND Area ACtion Plan on Tuesday 430th April 2024 at DBCL Stadium. As well as schools some proffessional have also expressed and intrest in coming ot the event after hearing about is. The number booked on to date is 115 deleagates. The Family Hub has held workshops with various professional to launch their digital Hub approach to sharing information with parent/carers and professionals. | Continue to enagage with stakeholders throughout the process
PAP 4.12 | Increase uptake of annual health checks through: | Carl Dawood |  | - List cleanse actions undertaken by all Halton GP practices - Practices with high and low uptake identified - Examples of good practice shared from high performing practices to aide those with lower uptake (N.B. low numbers support a very targeted approach) | List cleanse completed | 75% of adults with a learning disability (aged 14 or over) who are on a GP register, will have an annual health check. | Achieve national uptake targets. 2022/23 achievement - 76.6%
| - increase accuracy and completeness of GP registers |  | Q3 23/24 | [5 empty] | List cleanse actions undertaken by all Halton GP practices
| - identify and proactively support practices with low uptake, adopting best practice form other practices. |  | Mar 24 - Mar 25
| - promote LD Annual Health checks to young people and families to improve registration and uptake (Part of PAP 2) |  | Jan - Mar 25
PAP 4.13 | Undertake relevant Impact Assessments to inform the work, ensuring that plans / services enable participation, including to underserved populations | tbc | Informed by plans for other actions in PAP | Impact assessments undertaken and considered as part of design, decision making and implementation process, with oversight from the SEND Executive Group |  | 100% of services that are designed, re-designed, commissioned, de-commissioned, tendered will have a quality and equality impact assessment. | - Increased uptake of services from underserved population - measure tbc - Person reported experience measures - tbc - Person reported impact / outcome measures - tbc - Quality Impact Assessments / Equality Impact Assessments

## Priority 5
Priority 5 – Education Health and Care Plans
Ref | Actions (what we will do) | Owner | Timescale | Success criteria (how we know it's achieved) | Progress (what steps we have taken so far) | Outcome/impact (the difference this made) | Evidence (how we show this) | RAG | Progress since last meeting - SSIB (SEND Strategic Improvement Board) | Next steps
PAP 5.1 | CYP and Family Voice: Complete survey of parents/ carers/ families and CYP to appraise assessment experience and quality | C Finch/ Programme Lead | April 2024 (repeated 6 monthly) | Survey coproduced and published. Baselines established in assessment experience and quality | One survey already completed as par as part of DBV work. Expand on these to develop new survey to form baseline. SROs generating questions relative to their priority areas to help form the overall survey. | The partnership will possess detailed insight into the experience and views of CYP and their families on quality of assessment process and EHCP improved, guided by parent/carer/ CYP voice. Parents/CYP know they are listened to and are contributing to improvement activity | Baseline established via first survey by June 2024, in relation to experience of assessment and quality of new plans. By June 25, 25% improvement from initial baseline reported in the experience of assessment and quality of new plans via survey. By December 2025 a further 25% improvement reported in the experience of assessment and the quality of new plans via survey. regular monitoring in place to maintain improvements. By January 2026, the wider satisfaction survey shows that 51% of CYP and their families feel heard and effectively involved in the production of the EHCP. |  | Survey questions submitted to Emma P. Transformation liaising with Comms Team to determine best method of sharing with parents/carers and best report mechanism (and if this can feed into a dynamic dashboard) | Agree date for Survey to go live (can this be agreed at meeting on 8.04.24).
PAP 5.2 | i) Complete survey of parents/ carers/ families and CYP to appraise all elements of the SEND Area partnership relating to leadership visibility and satisfaction with general SEND Services across the Local Area Partnership | C Finch/ Programme Lead | April 2024 (repeated 6 monthly) | The partnership will possess detailed insight into the experience and views of CYP and their families on the effectiveness of Halton's leadership working and satisfaction with general SEND Services across the Local Area Partnership. Survey coproduced and published. Baselines established in understanding experiences of leadership working for improved outcomes and satisfaction with general SEND Services across the Local Area Partnership. Results of survey shared with all stakeholders via a number of workshops and engagement sessions and published on the Local Offer. Post Survey insight report submitted to Improvement Group. |  | The partnership will possess detailed insight into the experience and views of CYP and their families on the effectiveness of Halton's leadership working and satisfaction with general SEND Services across the Local Area Partnership. | Parents report improved satisfaction with general SEND Services across the Local Area Partnership (Education, Health, Children's Social Care) evidenced via responses from parents/carers and children and young people to SEN satisfaction survey. by December 2024 20% improvement. June 2025 25% improvement. Dec 2025 40% improvement. KPIs across all areas of SEND show at least 25% improvement by sept 2025. (baseline measures to be agreed and established) |  | Survey questions submitted to Emma P. Transformation liaising with Comms Team to determine best method of sharing with parents/carer and best report mechanism (and if this can feed into a dynamic dashboard) | Agree date for Survey to go live (can this be agreed at meeting on 8.04.24).
| ii) CYP and Family Voice: Complete survey of parents/ carers/ families and CYP to appraise assessment experience and quality |  | April 2024 (repeated 6 monthly) | Survey will be completed and results shared. Views of parents/ carers will be captured and feedback collated to informa plans for the future. Shared with (list stakeholders) | Programme Lead has commenced drafting of the survey. | Greater and detailed insight obtained into the experience and views of CYP and their families, in response to a comprehensive survey. Rich feedback obtained to improve practices. Quality of assessment process and EHCP improved, guided by parent/carer/ CYP voice. Parents/CYP know they are listened to and are contributing to improvement activity. | Baseline established via first survey by June 2024, in relation to experience of assessment and quality of new plans. By June 25, 25% improvement from initial baseline reported in the experience of assessment and quality of new plans via survey. By December 2025 a further 25% improvement reported in the experience of assessment and the quality of new plans via survey. regular monitoring in place to maintain improvements. By January 2026, the wider satisfaction survey shows that 51% of CYP and their famililes feel heard and effectively involved in the production of the EHCP. |  | Survey questions submitted to Emma P. Transformation liaising with Comms Team to determine best method of sharing with parents/carer and best report mechanism (and if this can feed into a dynamic dashboard) | Agree date for Survey to go live (can this be agreed at meeting on 8.04.24).
| iii) Develop and implement effective multi-agency and CYP, parent/carer feedback to be issued and evaluated following statutory assessment |  | 2024-06-01 | short survey sent following completion of every assessment. Feedback obtained on a regular basis and fed into improvement process to inform and influence practice | Scoping underway/ potential digital solution identified. DBV survey complete to assist in development of further survey | Feedback following each assessment improves insight into the quality of assessment and EHCP, and guides improvement activity via quality assurance process. Parents/CYP know they are listened to and are contributing to improvement activity. | by Jan 2025 50% of assessment/ new plans will be described as at least good by parents/ carers/ CYP in post assessment survey. By August 2025 65% of assessment/ new plans will be described as at least good by parents/carers/ CYP. By January 2026 90% of assessment/ new plans will be classed as at least "good" by parents/cares/ CYP. |  | Discussion with AS's team manager to determine best mechanism for sharing post assessment. | Need to establish recording and reporting mechanism. liaise with Debbie O'Connor to replicate process already in use in adults.
| iv) Co-produce and implement process to review and utilise feedback to shape and improve services |  | 2024-06-01 | Feedback Process written, signed off by Board, published and in use. | no progress towards this action yet | Regular and rich feedback to improve practice. Quality of assessment process and EHCP improved, guided by parent/carer/ CYP voice. Parents/CYP know they are listened to and are contributing to improvement activity. | by Jan 2025 50% of assessment/ new plans will be described as at least good by parents/ carers/ CYP in post assessment survey. By August 2025 65% of assessment/ new plans will be described as at least good by parents/carers/ CYP. By January 2026 90% of assessment/ new plans will be classed as at least "good" by parents/cares/ CYP. |  | Discussion with AS's team manager to determine best mechanism for sharing post assessment. | Need to establish recording and reporting mechanism. liaise with Debbie O'Connor to replicate process already in use in adults.
PAP 5.3 | Wider Service Review: Review the services and EHCP processes and paperwork to improve quality and timeliness of both statutory assessment and annual reviews. | C Finch | 2024-07-01 | Review completed | Review of processes undertaken | The Quality of EHCPs will be improved. Guidance on what good looks like and an will be published on the local offer. We will have understanding and agreement of what an optimum service delivery model looks like to measure against. Timeliness of assessment improved. Annual review response rates improved. | By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. by Jan 2025 50% of assessment/ new plans will be described as at least good by parents/ carers/ CYP in post assessment survey. By August 2025 65% of assessment/ new plans will be described as at least good by parents/carers/ CYP. By January 2026 90% of assessment/ new plans will be classed as at least "good" by parents/cares/ CYP. By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. By June 2025 90% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%. |  | QA processes progressing well. Envision 360 about to be launched. meeting held with principle EP, SA manager and STAs on processes around requests for assessment. and panel, to improve oversight and challenge. We want to ensure we are assessing only children who require it, to help improve efficiency. New process map in design phase. Scoping out digital solutions for EHCP assessment. Looking at existing capacity within synergy. Emma can provide verbal update on this. | Design process map for EHCP requests. Share update with schools. Update Local Offer. Benchmark exercise with other LAs re caseworker caseloads.
| Review and implement process for all EHCP outcomes to be signed off by health professionals, social care and education partners when plans are finalised. | C Finch/ S Nicholson/ K Gater/ K appleton(or DSCO) | 2024-06-24 | All plans will be signed off by each agency. A new porcess for sign off agreed and published. | Initial training completed by those signing off plans.Envision 360 purchased, and initial training completed. Further staff training scheduled. | EHCP quality will be improved, being a genuinely multi-agency assessment | By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. by Jan 2025 50% of assessment/ new plans will be described as at least good by parents/ carers/ CYP in post assessment survey. By August 2025 65% of assessment/ new plans will be described as at least good by parents/carers/ CYP. By January 2026 90% of assessment/ new plans will be classed as at least "good" by parents/cares/ CYP. By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. By June 2025 90% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%. |  | This is now happening. Action complete.
PAP 5.4 | i) Complete benchmark and analysis exercise of SEND Assessment Team to determine optimum delivery model. | E Power | 2024-05-24 | Benchmark analysis complete and optimum delivery model understood | Benchmark exercise scoped out and commenced | greater insight into the optimum model of SEND assessment delivery. Optimum team model can be designed and put in place. We will have understanding and agreement of what an optimum service delivery model looks like to measure against. Timeliness of assessment improved. Annual review response rates improved. | By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. by Jan 2025 50% of assessment/ new plans will be described as at least good by parents/ carers/ CYP in post assessment survey. By August 2025 65% of assessment/ new plans will be described as at least good by parents/carers/ CYP. By January 2026 90% of assessment/ new plans will be classed as at least "good" by parents/cares/ CYP. By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. By June 2025 90% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%. |  | No progress to date | Send questionaire to stat neighbours to determine caseloads.
| ii) SEND Assessment Team structured reviewed and redesigned following benchmark exercise, considering options to increase capacity | C Finch | 2024-09-24 | Assessment Team Model amended for optimum delivery | Casework Stress test exercise underway | greater insight into the optimum model of SEND assessment delivery. Optimum team model can be designed and put in place. We will have understanding and agreement of what an optimum service delivery model looks like to measure against. Timeliness and quality of assessment improved. Annual review response rates improved. | By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. by Jan 2025 50% of assessment/ new plans will be described as at least good by parents/ carers/ CYP in post assessment survey. By August 2025 65% of assessment/ new plans will be described as at least good by parents/carers/ CYP. By January 2026 90% of assessment/ new plans will be classed as at least "good" by parents/cares/ CYP. By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. By June 2025 90% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%. |  | This will comence once scoping is complete. | Design process map for EHCP requests. Share update with schools. Update Local Offer. Benchmark exercise with other LAs re caseworker caseloads.
| iii) Halton LA will provide a clear plan to ensure that it has in place a permanent, suitably trained, SEN case work team of sufficient capacity to enable the effective delivery of the statutory EHC needs assessment and maintenance, including the annual review | C Finch | 2024-07-24 | benchmark analysis complete, team redesigned following benchmark. Recruitment and retention plan written and agreed. | Benchmark exercise scoped out and commenced | Timeliness and quality of EHCPs will be improved. greater insight into the optimum model of SEND assessment delivery. Optimum team model can be designed and put in place. We will have understanding and agreement of what an optimum service delivery model looks like to measure against. Timeliness of assessment improved. Annual review response rates improved. | By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. by Jan 2025 50% of assessment/ new plans will be described as at least good by parents/ carers/ CYP in post assessment survey. By August 2025 65% of assessment/ new plans will be described as at least good by parents/carers/ CYP. By January 2026 90% of assessment/ new plans will be classed as at least "good" by parents/cares/ CYP. By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. By June 2025 90% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%. |  | QA processes progressing well. Envision 360 about to be launched. meeting held with principle EP, SA manager and STAs on processes around requests for assessment. and panel, to improve oversight and challenge. We want to ensure we are assessing only children who require it, to help improve efficiency. New process map in design phase. Scoping out digital solutions for EHCP assessment. Looking at existing capacity within synergy. Emma can provide verbal update on this. This work cannot commence until scoping of processes and benchmarking is complete | Design process map for EHCP requests. Share update with schools. Update Local Offer. Benchmark exercise with other LAs re caseworker caseloads.
| iv) Training completed by all advice givers, to ensure high quality advice across services | S Nicholson | 2024-07-24 | Training completed by 100% of advice givers across all services | Training designed, method of delivery etsablished, training dates agreed | Quality and timeliness of EHCPs will be improved | By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. |  | Training has been rolled out already to schools. | Further training for all advice givers, inclusing health and social care to be designed.
| v) Development of annual review best practice model and dissemination to frontline teams. | C Finch | 2024-09-24 | Best practice model disseminated to all stakeholders | Best practice model scoping underway | The quality and experience of annual reviews will be improved | By December 2025, 25% improvement reported in the experience and satisfaction of CYP and their families in relation to annual reviews-via survey. By June 2025 90% of annual reviews are completed within statutory timescales. |  | Not yet started | Through link with DfE, identify LAs who are operating best practie re ARs. complete EHCP digitisation work.
| vi) Stakeholders ensure that EHCP annual reviews are prioritised and scrutinised from Year 9 and above. Annual reviews will inform future planning in preparation for adulthood. | H Bell/ S Nicholson. D Tierney | 2024-09-24 | Annual Reviews inform Preparation for Adulthood. The Transition team will attend year 11, 12 and 13 EHCP reviews. The transition team’s criteria accepting referrals at year 11 is agreed and published. The transition Team will attend Annual REviews from year 9 onwards for children with Significant and Complex Needs (CYP likely to require adult services).Re: EHCP YP with a diagnosed mental health disorder as their primary need with an EHCP in place, the mental health team will attend EHCP reviews from the age of 16, if referred into the service. Crissi escalation process designed, agreed and published. | The Transition team have reached out to educational settings and partners to determine people who are on EHCPs, with a view to attending reviews and being preventative and tracking our young people. Lists obtained from education settings which we screen, with a view to contribute to the meetings going forward. Meeting taken place regarding scoping for an all age disability service. The Transitions team in porcess of implementing an online referral form, to enable stakeholders to refer in timely to the team to ensure young people have the appropriate support in preparing for adulthood from year 11. | CYP with SEND are well prepared for adulthood from the earliest reasonable opportunity, benefitting from a holistic, multi agency support arrangement. . The pillars of preparing for adulthood are identified and planned for, at the earliest opportunity working in partnership with the young person, their families/carers and stake holders Transition process are significantly improved. Relationships between CYP and their families and :A support services into adulthood are significantly improved. Any arising issues are escalated and resolved quickly and effectively. | By Dec 2024, 25% improvement reported in the transition experience of CYP and theif families from y9 onwards. By June 2025, move than 50% of respondents report feeling Well prepared for adulthood. |  | Not yet started | Meet with AS manager and Háf to determine best way to progress this.
PAP 5.5 | Quality Assurance: Implement Audit tool, Envision 360, for EHCP and Annual reviews | S Nicholson | 2024-04-24 | Envision 360 will be in use. All staff will have completed the necessary training. | Envision 360 purchased, and initial training completed. Further staff training scheduled. | EHCP quality will be improved | By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. by Jan 2025 50% of assessment/ new plans will be described as at least good by parents/ carers/ CYP in post assessment survey. By August 2025 65% of assessment/ new plans will be described as at least good by parents/carers/ CYP. By January 2026 90% of assessment/ new plans will be classed as at least "good" by parents/cares/ CYP. By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. By June 2025 90% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%. |  | Almost complete. Envision training being completed. | Implement and embed.
PAP 5.6 | Explore the benefits of the appointment of a stand-alone DSCO | Z Fearon/ K Appleton | TBC | DSCO in post | DSCO JD and Jb spec scoping complete. Recruitment and funding options being explored. | All EHCPs will contain advice from Social care, following social care assessment. Advice provided by Social Care will be timely and of good quality. Social Care will play an active role and be well represented in Statutory Panels. | By June 2026 100% of requests for advice for EHCP will result in social care assessment and advice- Date to be comfirmed |  | CF engaged with DSCO session *(handouts and PP available if required) | Consider how this post could be resourced and where would sit in structure. Recruitment.
PAP 5.7 | i) Scope out SEND portal options with a view to implementation | E Power/ C Finch | 24th March | Most effective portal identified and purchased. SEND portal Implemented. | Scoping underway/ potential digital solution identified | EHCP process efficiency improved. Timeliness of statutory assessment and Annual reviews improved. CYP and their families will enjoy an improved assessment experience. CYP and their families will feel more involved in the assessment process. | By June 2025 75% of respondents will describe their EHCP assessment experience as good. By June 2025, 75% of respondents will report feeling involved and heard during the assesment process. By June 2025 95% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%.
| ii) SEND portal training completed by all stakeholders | C Finch | 24th December | Training completed by 100% of advice givers across all services | Scoping underway/ potential digital solution identified | Timeliness and quality of EHCPs will be improved. | By June 2025 75% of respondents will describe their EHCP assessment experience as good. By June 2025, 75% of respondents will report feeling involved and heard during the assesment process. By June 2025 95% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%.
| iii) SEND Portal in full use | C Finch | 25th January | Portal in full use | Scoping underway/ potential digital solution identified | Timeliness and quality of EHCPs will be improved | By June 2025 75% of respondents will describe their EHCP assessment experience as good. By June 2025, 75% of respondents will report feeling involved and heard during the assesment process. By June 2025 95% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%.