## RAG Rating
Status | Definition
Grey | Action not started.
Blue | Action completed and signed off,
Green | Action on target.
Amber | Action delayed and likely to miss completion date.
Red | Action significantly delayed and has missed completion date (new completion date required) or, No actions made to progress.

## Priorities
Areas for priority action | Resonsible Body | Senior Responsible Officer (SRO)
Priority 1 - Strategic Oversight and Governance
Leaders at Halton local authority and the NHS Cheshire and Merseyside ICB should cooperate at pace to improve the shared strategic oversight, governance, support and challenge to drive improvements to meet the needs of children and young people with SEND in Halton. | Halton Borough Council and NHS Cheshire and Merseyside Integrated Care Board (ICB) | Education, Inclusion & Provision (HBC)
Priority 2 - Cohesive communication / joined up systems
Leaders in the local authority, ICB and education, health and social care providers should improve the efficiency and quality of their information gathering and sharing processes to ensure that children’s and young people’s needs are understood accurately and met more swiftly and effectively through coordinated approaches. | Halton Borough Council and NHS Cheshire and Merseyside Integrated Care Board (ICB) | Mike Stapleton Chambers - Senior School Quality Assurance Officer DBV SEND Programme Lead (HBC)
Priority 3 – Joint Commissioning
Leaders across education, health and social care should improve the joint commissioning of services to ensure that children, young people and their families receive sufficient support to have their needs met effectively. | Halton Borough Council and NHS Cheshire and Merseyside Integrated Care Board (ICB) | Lee Ellis - Head of Service Commissioning (HBC)
Priority 4 – Early identification of need and access
Leaders across education, health and social care should urgently improve the early identification of needs and access to specialist health pathways, including the neurodevelopmental assessment pathway and speech and language therapy and the support available, while children and young people wait. | Halton Borough Council and NHS Cheshire and Merseyside Integrated Care Board (ICB) | Philip Thomas - Associate Director Transformation and Partnerships Halton (ICB)
Priority 5 – Education Health and Care Plans
Leaders across education, health and social care should improve the timeliness of new EHC plans and updates to EHC plans following the annual review process, so that, if appropriate, children and young people receive an effective EHC plan within statutory timescales. | Halton Borough Council and NHS Cheshire and Merseyside Integrated Care Board (ICB) | Charlotte Finch - Head of Service, SEND (HBC)

## Priority 1
Priority 1 - Strategic oversight and Governance
Ref | Actions (what we will do) | Owner | Timescale | Success criteria (how we know it's achieved) | Progress (what steps we have taken so far) | Outcome/impact (the difference this made) | Evidence (how we show this) | RAG | Progress since last SSIB | Next steps | Slippage with reasons
1.1 | Establish Halton SEND Improvement Board | Martin West | 2024-03-01 | Board Meetings diarised for 2024/25 | Tracy Ryan diarising Board Meetings. ToRs agreed Membership agreed Governance and Reporting agreed | The Halton SEND Strategic Improvement Board brings together system senior leaders with a shared strategic vision, direction and challenge, are accountable for, oversee and monitor the delivery of the Halton SEND Strategic Plan, SEND Improvement Plan and SEND Local Area inspection Recommendations. | Terms of Reference Governance and Reporting algorithm Membership from all partner organisations Schedule of meeting dates Schedule of Reporting
|  |  | 2024-03-01 | Terms of reference agreed by partners
|  |  | 2024-03-01 | Membership agreed
|  |  | 2024-04-01 | Independent Chair recruited.
|  |  | 2024-03-01 | Governance and Reporting mechanisms in place
1.2 | Establish Halton SEND Delivery GroupImprovement Board | Martin West | 2024-03-01 | Delivery Group Meetings diarised for 2024/25 | Tracy Ryan diarising Board Meetings. ToRs agreed Membership agreed Governance and Reporting agreed. | The Halton SEND Delivery Group will provide robust multi agency oversight for the delivery of services across the SEND partnership and the programme of change required to provide an outstanding service to children and young people with Special Educational Needs. The Delivery Group will also have responsibility for the delivery of the recommendations outlined in the Halton local Area partnership SEND Inspection. The Delivery Group will provide key governance ensuring pace, challenge and oversight for all aspects of SEND improvement across the partnership. | Terms of Reference Governance and Reporting algorithm Membership from all partner organisations Schedule of meeting dates Schedule of Reporting
|  |  | 2024-03-01 | Terms of reference agreed by partners
|  |  | 2024-03-01 | Membership agreed
|  |  | 2024-03-01 | Joint H&SC Chairs recruited.
|  |  | 2024-03-01 | Governance and Reporting mechanisms in place
1.3 | Establish Halton Priority Workstreams | Charlotte Finch and Philip Thomas | 2024-03-01 | Senior Responsible Officers leading 5 Priority Action Plan areas. | SRO's identified for all 5 Priority Areas. Action Plans developed and submitted and approved by Ofsted/DfE Governance Structure in Place. | Halton SEND Priority Workstreams will ensure the operational delivery of the Halton SEND Strategy and Improvement Plan requirements. The SRO's will be accountable to and report to the Delivery Group and by exception to the Improvement Board on progress, issues and challenges. The Workstream SROs will be accountable for the delivery of their PAP action plan. | Workstream Priority Action Plans Governace and Reporting algorithm Meeting schedule Halton SEND Integrated Performance Dashboard
|  |  | 2024-03-01 | Each PAP has a robust action plan in place with clearly identified leads, timescales, outomce measures and Evidence base.
|  |  | 2024-03-01 | All 5 PAP areas have diarised meetings scheduled for 2024/25
|  |  | 2024-03-01 | Clear lines of governance and reporting are in place to Halton SEND Delivery Group and Halton SEND Improvement board.
|  |  | 2024-06-01 | Establish SEND Integrated Performance Dashboard Workstream
1.4 | Establish a SEND Programme Management Office | Charlotte Finch | 2024-05-01 | Recruit a PMO Manager | Agreed joint recruitment of PMO Manager for 2 year fixed term contract. JD and PS Job Evaluation completed by HBC. CF completed the amendment to establishment. Job advert written. will go live week beginning 15/07 | Halton SEND Partnership will have a fully functioning Programme management Office in Place. | Workforce in place. Full suite of reporting templates/reports. Governance Structure Reporting and Meeting Schedules Integrated performance Dashboard. Meeting schedule of Halton SEND SIB and Halton SEND Delivery Group circulated to all members and SROs to ensure reporting submissions achieved. Meeting schedule established. |  | 03/04/24 - Draft JD/PS complete and job has now been evaluated SEND PMO post advertised with closing date 30/08/2024. | Interview SEND PMO Lead scheduled 06/09/2024.
|  |  | 2024-05-01 | PMO human resource support and Administration in place. |  |  |  |  | Have interim support identified | Consideration at Delivery Group for administration support is required including financial resource.
|  |  | 2024-04-01 | Shared Central SEND repository of information in place.
|  |  | 2024-04-01 | Standardised Report format in place |  |  |  |  | All Action Plans reviewed and formatted for consistency and tracking. | Approval of PAP Action Plan tracker at HSSIB 17/04/2024
|  |  | 2024-04-01 | Standardised Highlight Report format in place.
|  |  | 2024-03-01 | Clear governance and Reporting in place
1.5 | Complete survey of parents/ carers/ families and CYP to appraise all elements of the SEND Area partnership relating to leadership visibility and satisfaction with general SEND Services across the Local Area Partnership | C Finch/ Programme Lead | April 2024 (repeated 6 monthly) | Survey coproduced and published. Baselines established in understanding experiences of leadership working for improved outcomes and satisfaction with general SEND Services across the Local Area Partnership. | One survey already completed as part of DBV work. SROs generated questions relative to their priority areas to help form the overall survey. Survey went live 1st June 2024, and closed 30th June 2024. Evalutaion currently being undertaken and will be shared initially with the SROs, then Delivery group and then SSIB. | The partnership will possess detailed insight into the experience and views of CYP and their families on the effectiveness of Halton's leadership working and satisfaction with general SEND Services across the Local Area Partnership. | Parents report improved satisfaction with general SEND Services across the Local Area Partnership (Education, Health, Children's Social Care) evidenced via responses from parents/carers and children and young people to SEN satisfaction survey. by December 2024 20% improvement. June 2025 25% improvement. Dec 2025 40% improvement. KPIs across all areas of SEND show at least 25% improvement by sept 2025. (baseline measures to be agreed and established) |  | Co-produced survey was issued 1st June 2024, closed 30th June 2024, and included questions provided by SROs and other agencies. Evaluation currently underway. | Evaluation of survey to be undertaken, shared with SROs, Delivery Board, and finally SSIB | decision was taken to spend more time co-producing the survey at Improvement Board. this casued delay, which was considered an acceptable delay, in order to ensure survey was properly coproduced.
| Complete survey of parents/ carers/ families and CYP to appraise all elements of the SEND Area partnership relating to leadership visibility and satisfaction with general SEND Services across the Local Area Partnership | C Finch/ Programme Lead | April 2024 (repeated 6 monthly) | Results of survey shared with all stakeholders via a number of workshops and engagement sessions and published on the Local Offer. Post Survey insight report submitted to Improvement Group. | One survey already completed as par as part of DBV work. Expand on these to develop new survey to form baseline. SROs generating questions relative to their priority areas to help form the overall survey. Programme Lead has commenced drafting of the survey. | The partnership will possess detailed insight into the experience and views of CYP and their families on the effectiveness of Halton's leadership working and satisfaction with general SEND Services across the Local Area Partnership. | Parents report improved satisfaction with general SEND Services across the Local Area Partnership (Education, Health, Children's Social Care) evidenced via responses from parents/carers and children and young people to SEN satisfaction survey. by December 2024 20% improvement. June 2025 25% improvement. Dec 2025 40% improvement. KPIs across all areas of SEND show at least 25% improvement by sept 2025. (baseline measures to be agreed and established) |  | An analysis of the surveys will be reported via a Board paper and also a powerpoint presentation. this summary analysisi will be shared on the local offer, at SEND Delivery Group and Improvement Board, It will also be shared with PCF and at Headteacher and SENDco briefings. | Stakeholder Event required and feedback on survey results delivered. Publish results on Local Offer website. Post Survey insight report submitted to HSSIB 14th August 2024.
1.6 | Halton SEND Strategy and action plan reviewed and revised in line with Ofsted Inspection and PAP 2022 - 2025 | Denise Roberts | 2024-03-01 | A refreshed SEND Strategy and accompanying action plan coproduced, agreed and published. | Halton SEND Strategy 2022 - 2025 has been refreshed to include the findings and recommendation of the Halton SEND Local Area inspection | 1) Strategic leaders across the Local Area Partnership work well/collaboratively together to set a consistent direction for SEND improvement. 2) Revised priorities are agreed/determined based on recent inspection outcomes and are known and understood across the partnership. 3) Children, families and stakeholders across Halton are aware of the SEND Strategy, and what the partnership are trying to achieve. 4) That Children, young people and families will benefit from the improvements across all sevices | Revised Halton SEND Strategy 2021 - 2025. Priority Action Plan and Governance published on Local Offer Website.
1.7 | Halton SEND Strategy 2025 - 2028 to be co-produced | Charlotte Finch | 2024-05-01 | Halton SEND Strategy Working Group established. | working group identified, but no meetings taken place yet. SEND Sufficiency strategy has been prioritisied for completion. that is due for publication in September. ONce that is complete work will start at pace on the SEND strategy. Whilst some actions are delayed, we fully anticipate meeting the overall deadline and publishing the new Strategy by march 25. | Halton SEND Strategy 2025 - 2028 will have been co-produced with CYP, their carers and families. Our approach will be grounded in what works best to improve outcomes for children and young people so that they can have the best future possible and thrive as part of our local community. We will have been efficient and evidneced based in prioritising what we know we need to focus on to provide the right level of support through education, health and care. | Halton SEND Strategy 2024 - 2028 published. Meetings, workshops minutes and agendas. Vocie of CYP, Parents and Carers. |  | none | book dates from September onwards for working group. | meetings delayed as SEND Strategy ius not due for delivery until March 25. SEND Suffieciency strategy had to be given priority.
|  |  | 2024-05-01 | Equal partner membership established |  |  |  |  | none | Share meeting dates with membership.
|  |  | 2024-05-01 | Joint leadership with Halton Parent and Carers Forum in Place |  |  |  |  | joint leadership agreed but no meetings taken place to date | as above
|  |  | 2024-05-01 | Bi-Monthly workshops diarised to ensure communication, engagement and participation in the development of the strategy. |  |  |  |  | no meetings yet diarised | diarise meetings
|  |  | 2024-06-01 | Clerly identified Aims, Objectives and Outcomes identified |  |  |  |  | aims and objectives to be agreed at the first meeting. these will be shared across the CYP, the SEND Sufficiency Strategy and the AP strategy. | identify Aims and Objectives of the working group and include them in TOR
|  |  | 2024-06-01 | Integrated SEND Dashboard used to identify priorities and monitor improvements. |  |  |  |  | SEND Dashboard working group now established and great progress made to narrow down data fields. DAshboard almost complete All SROs have identififed which data sets are reqruired to measure performance against the action plan. | Use the Dashboard to guide strategy. | Data dashboard delayed due to difficulty narrowing down the fields. this has now been rewsolved. No further slippage anticipated.
|  |  | 2024-11-01 | Draft Strategy coproduced
|  |  | 2024-12-01 | Draft Strategy delivered to Halton Parent and Carer Forum for Approval
|  |  | 2025-02-01 | Draft Strategy delivered to Halton SEND Strategic Improvement Board for Approval
|  |  | 2025-03-01 | Halton SEND Strategy 2025 - 2028 delivered to Halton Health and Wellbeig Board for Apporval and sign off.
|  |  | 2025-03-01 | Halton SEND Strategy 2025 - 2028 published on Local Offer Website
1.8 | Leaders and stakeholders in Halton will ensure there is an Alternative Provision Strategy developed and informed by stakeholders | Charlotte Finch/ L Corlett/ K Greaves | 2024-09-24 | Halton Alternative Provision Strategy and Alternative Provision offer co-produced with all system partners. | AP Strategy in development. First draft completed and shared with stakeholder group and also Slip Partners from Blackburn with Darwen. It was agreed that this strategy documnet is not fit for purpose and could not be used. the strategy lacked focus, coherence and had not been coprodcued. Further co-production and financial modelling required along with a new approach to drafting the plan. A new consultant has been asked to pick up the work and complete the new strategy by September. he has access to the work done so far. He reports that a coherent strategy can be produced by September. | AP Strategy and model offer will be known by stakeholders. AP offer increases educational options. More CYP will remain in education. Per ex and Fixed suspensions reduced. | Halton Perm ex reduced to be at least in line with regional average- a reduction of 0.03% by July 2025. By Sept 24 Satisfaction survey tells us that 51% of CYP/ families are aware of AP offer in Halton. By June 25 satisfaction survey indicates that 51% of CYP/ families are aware of AP offer in Halton. |  | New AP lead commissioned to complete the strategy. Meeting taken place to agree timescale for delivery. Delivery schedule of September agreed. |  | April deadline was not realistic as Action Plan only submitted to DfE in March. September deadline agreed. Initial Strategy was drafted but due to quality of the draft Statregy document. It could not be used and therefore significant additoinal work is required to bring the document up to standard.
AP Strategy submitted to Halton SEND Improvement Board for approval.
AP Strategy submitted to Halton Health and Wellbeing Board for approval and sign off.
AP Strategy published on Halton Local Offer website.
1.9 | Develop a Halton SEND Integrated Performance Dashboard | Michelle Creed | 2024-03-24 | Establish Halton SEND Integrated Performance Dashboard Workstream | Invitations to workstream sent out and meetings have taken place. now narowed down the data sets, so the dashboard has no more than 25 data points, by which to monitor and measure performance. a meeting with the SROs helped to narrow down the number, and ensures that we are using the most useful data for each priority area. | Halton SEND Strategic Improvement Board, Halton SEND Delivery Group and partners will have an evidenced based perfomance dashboard that will identify the quality, effectiveness and experience of services provided to CYP and their families. | Halton SEND Integrated Performance Dashboard |  | Workstream established. Identified - Linda Edwards, Louise Owen C&M ICB - Paul Moore, Scott Middlehurst HBC Education - Julia Rosser HBC PH as leads for development of Integrated Dashboard.
|  | Michelle Creed | 2024-03-24 | Diarised Meetings in place | Agreed frequency of meetings | Task and Finish Group established. | Halton SEND Integrated Performance Dashboard |  | All meetings diarised and work to narrow down the data points complete. the proposed Dashboard will be presented to the Delivery Group for sign off and then become live.
|  | Charlotte Finch | 2024-05-24 | Recruit Halton LA SEND Data Analyst | Approved Data Analyst post at Halton SEND Delivery Group | Halton SEND Data Analyst in post | Halton SEND Data Analyst in post |  | Post Agreed and funded. Job Description agreed. 06/05/2024 - Post recruited to successful candidate in post.
|  | All | 2024-04-01 | Review Council for Disabled Children recommended indicators, other LA dashboards and current indicatros collected. | SRO met with Business Intelligence Analysts | Ensure consideration of full suite of indicators has been reviewed for impact and outcome measures. | Agreed set of Halton SEND KPIs agreed by partners |  | Reviewed Council for Disabled Children, Sefton LA, Wirral LA, Kingston LA, Salford LA indicators. Long list of indicators now collated and removal of duplication underway.
|  | Louise Owen | 2024-04-24 | Working with BI partners review national and local indicators and produce long list. | Indiactos reviewed from Council for Disabled Children, Trafford, Salford, Liverpool, Sefton and Halton areas. | Long list of KPIs established | Long list of KPIs established |  | 06/05/2024 - Long list of indicators drafted and circulated to partners and discussed at SEND Delivery Group.
|  | All | 2024-05-24 | Agree suite of indicators to be used for the Halton Integrated Performance Dashboard with SROs to ensure all priority actions outcomes can be measured. | 06/05/24 - Circulated Long List to SROs for review against SEND Inspection requirements and SEND overall Improvement Plans to check, what is missing, anything needed to add in, any comments and to ensure that the Inspection outcomes can be evidenced. Due date for response 15/05/24. No feedback recieved from SROs. BI analysts continue to develop. 04/06/2024 - BI Analysts undertaken further work to ensure no duplication of indicators present, highlighting all indicators which currently have accessible data and by the source. Redrafted KPI set and redistributed to SRO's for review and sign off to enable the build of the 1st Draft Integrated Dashbaord for the HHSIB on 20th June 2024. | Halton SEND Integrated Performance Dashboard | Halton SEND Integrated Performance Dashboard |  | 26/06/2024 - Meeting scheduled to progress on 03/07/2024 draft to be submitted to SEND Delivery Group 27/07/2024 for discussion and next steps. 03/07/24 - Meeting with Data Analysts and SROs took place and agreed: - Recircualte copies of SEND LAP Inspection Report, Current Dashboard and Narrative Template for consideration. - All SROs (PAP 3,4 and 5) to review the SEND Inpsection Report and the current dashboard indicators and decide the key indicators that will deonstrate improvments and if any are missing. Aim for maximum of 25 indicators. 11/07/24 - Final KPIs submitted to be converted into presentation style view (charts/graphs) and recirculated to SRO's 16/07/24 - SROs updated the narrative against the KPIs 19/07/24 - Report to be prepared for Delivery Group 24/07/24 31/07/2024 - Halton SEND Delivery Group Agreed: - 26 key performance indicators that will evidence improvements in service provision against the Halton Local Area Partnersip Inspection recommendations. - the full dashboard be presented at both Delivery GRoup and Improvement Board for assurance and challenge. - for sustainability that the LA SEND Business Analyst produce the reports for the above meetings and act as the central contact, supported by partnership BI Leads. - the Halton CYP, Parent and Carer survey findings would be presented to the Board in August 2024 to establish the baseline position. Thereafter, the information received will be reviewed alongside the ‘I’ indicators: • I feel supported • I feel sage • I am included and active in my local community • I am able to learn • I am in control of my life And this information will be refreshed 6 monthly to ensue the qualitative data is reviewed against outcomes for CYP, their Parents and Carers
|  | All | 2024-05-24 | Consult with system partners on suite of indicators | Consultation at Halton SEND Stratgic Improvement Board to take place to ensure wider system leader oversight and comments to enable 2nd draft of Dashboard to be developed. Need to ensure it meets the Board requirements and has grip and conrol over performance. | Halton SEND Integrated Performance Dashboard | Halton SEND Integrated Performance Dashboard |  | 20/06/2024 Attended the Halton SEND Strategic Improvement Board and the Board were asked to: 1) note the significnant progress made to date in the development of the Halton SEND Integarted Performance Dashboard. 2) Task the SEND Delivery Group to identify subject matter expertise to support the Business Intelligence Alalysts in finessing the indicators to the Board requirements. 3) Agree the full SEND Dashboard be managed by the SEND Delivery Group and reported by exception to the Board 4) Agree to recieve the qualitative data via the 'I' statements following the outcome of the SEND survey findings. All recommendations approved. Next Delivery Group 24/07/2024 31/07/2024 - System partners consulted and KPI's presented and approved at Halton SEND Delivery Group on 24/07/24
|  | Louise Owen | 2024-05-24 | Draft Halton SEND Integrated Performance Dashboard submitted to SROs for comments and draft approval | This stage is delayed due to disagreement about the correct datapoints. this now resolved and 1st draft will be presented to HSSIB in June 2024 and then circulated to SRO's for comment and further iteration. | Halton SEND Integrated Performance Dashboard | Halton SEND Integrated Performance Dashboard |  | Further draft circulated to SROs 26/06/2024 for consideration and meeting schedule 03/07/2024 with Business Analysts and SROs to define indicators in preparation for Delivery Group meeting on 27/07/2024. Further drafts circulated to SRO's 05/07/24, 16/07/24, 17/07/24 31/07/24 - Final submission of KPIs agreed by SRO's and presented to Halton SEND Delivery GROup and approved on 24/07/24 |  | Slippage due to inability to narrow down data points into a manageble number. that now resolved and 27 data points identified.
|  | Linda Edwards Louise Owen | 2024-07-25 | Draft Halton SEND Integrated Performance Dashboard submitted to Halton Delivery Board for further consideration, refinement and approval |  | Halton SEND Integrated Performance Dashboard | Halton SEND Integrated Performance Dashboard |  | 31/07/24 - KPI's Approved at Halton SEND Delivery Group on 24/07/24 | Paper to be presented to Halton SEND Strategic Improvement Board on 14/07/24 to final sign off. Halton SEND Integrated Dashboard presentation style for Board to include KPI performance and narrative from responsbile leads.
|  | Mike Stapleton Chambers | 2024-06-24 | Develop Halton SEND Data Sharing Agreement PAP 2 Leading | Scott Middlehurst (Halton IT ) is working with partners to agree way forward for joined up systems work and then IT will proceed with its creation. Following Synergy Web demonstration, task and finish group to be set up to agree the requirements for new case management system for SEND. This will design and implement a new system aligned to both national and local policies and timeframes. Data sharing will become part of this. | Halton SEND Integrated Performance Dashboard | Halton SEND Integrated Performance Dashboard |  | 15/05/24 - Michelle Creed connected Rob Foster, Digital Lead for One Halton and Mike Stapleton -Chalmers, SRO PAP 2 to ensure alignment with system digital and data sharing under One Halton workstreams. June 2024 - synergy Web task and finish group established. Data sharing agreements will be aligned to this. July 2024 - Meeting with ICB and LA leads to discuss One Halton Data Sharing requirements from a strategic perspective to enable an integrated approach. | Awaiting Synergy Implementation.
|  | Michelle Creed | 2024-08-14 | Final working version SEND Integrated Performance Dashboard completed and approved by HSSIB |  | Halton SEND Integrated Performance Dashboard | Halton SEND Integrated Performance Dashboard |  | 31/07/24 - Business Intelligence Analysts met and agreed format of reporting style with narrative for Board. Preparation for presentation at Board on 14/08/24 on schedule. - Draft paper produced for Board. 14/08/24 - Halton SEND Strategic Improvement Board cancelled and revised date of 12/09/2024 diarised. 28/08/2024 - Michelle Creed handover to Paul Moore of Performance Dashboard to ensure sustainability and central point of data collection. 16/09/2024 - Halton SEND Integrated Dashboard presented to the SEND Strategic Improvement Board on 12/09/2024 and it was accepted and signed off by the Board. Consequentially, the risk registered was updated, hence, this was deemed as achieved. - Commendations for the team for putting the dashboard togetherwere given. - Board were happy that the dashboard will help to track performance and uncover the areas where there are issues that required urgent attention. - Board pleased with the inclusion of the escalation report by the SROs that succinctly present current issues, the causes and what is been done to address the issues. - They agreed that based on the data in dashboard, our performance requires improvment and so the data should be treated as baseline. Moving forward comparision against the National benchmarks and the set targets will be required.

## Priority 2
Priority 2 - Cohesive communication / joined up systems What do we want to achieve? Leaders in the local Authority, ICB and education, health and social care providers will improve the efficiency and quality of their information gathering and sharing processes to ensure that children and young peoples needs are understood accurately and met through a swift coordinated approach
Ref | Actions (what we will do) | Owner | Timescale | Success criteria (how we know it's achieved) | Progress (what steps we have taken so far) | Outcome/impact (the difference this made) | Evidence (how we show this) | RAG | Progress since last meeting - SSIB (SEND Strategic Improvement Board) | Next steps | Slippage with reasons
PAP 2.1 | Complete survey of parents/ carers/ families and CYP to appraise all elements of the SEND Area partnership relating to Communication, Coproduction, Joint Working, the Local Offer and Information Sharing, to gather a performance baseline | C Finch/ Programme Lead | April 2024 (repeated 6 monthly) | - Survey coproduced and published. Baselines established in Co-production, Communication, Information Sharing and the Local Offer. - Results of survey shared with all stakeholders via a number of workshops and engagement sessions and published on the Local Offer. Post Survey insight report submitted to Improvement Group. "We Said, We Did" Outcome report published - so CYP/ Families can see how their input is shaping Service | - One survey already completed as par as part of DBV work. Expand on these to develop new survey to form baseline. SROs generating questions relative to their priority areas to help form the overall survey. Programme Lead has commenced drafting of the survey. June 24 - Survey circulated July 24 - Survey circulated, and closing date has now passed. Meetings have been held regarding analyse of survey and how the findings will be disturbed Survey has highlighted a major weakness around communications whilst on wating list for services. There is also a need around advice and support access. Many parents reported they weren’t happy with the level of communications they receive. Individual comments made highlighted the services where communication was an issue. | - The partnership will possess detailed insight into the experience and views of CYP and their families on the effectiveness of Halton's Communication, Coproduction, Joint Working, Local Offer and Information sharing. feedback from CYP and Families will be used to guide, influence and shape both strategy and operational practice. - CYP and their families will know that their views are influencing and shaping strategy and operational practice. CYP and their families will have increased confidence that their views are central to strategic design- via the publication of "We said, We did" outcome report. | - Published survey outcomes. Post Survey Insight Report. “You said, We did" Outcome Report. By June 2025, at least 51% of CYP and their families will tell us via survey that their input is sought, and used to guide, shape and influence strategy and operations | On target | - This action is underway. - Questions sent to Emma with help of Tracy Ryan | Awaiting Survey to be agreed and sent out
PAP 2.2 | Relaunch the Coproduction Charter and implement | Mike Stapleton-Chambers School Improvement Officer Tracy Ryan Policy Officer | 2024-07-01 | - Co–production charter/Strategy shared with all parents/carers, children and young people, services and settings, through training, workshops, and focus groups and published on the local offer. - Workshops completed to embed the co-production charter. | - Created a Co-Production Team from a range of stakeholders at all levels who agreed this action plan together. - Soft launch of co-production charter completed in November 2022. June 24 - Tracy Ryan to update Co-production Charter re new Executive Director, change to SEND Strategic Improvement Board and include Lundy Model/NHS Model. July 24 - Review and Co-production page for the launch of the Charter digitally available on the Local Offer. Refreshed Charter published. Strategy agreed for September digital launched followed by physical in person launch at Family Hub Conference in October. | - Children, young people and their families are confident that their voices are heard and drive change at the most fundamental and strategic levels. - Full and effective use is made of digital systems and children, young people and their families are empowered to take ownership of their needs as a result. | - By Jan 2025 50% of parents/ carers/ CYP report that they feel involved and listened to (via survey). - By August 2025 65% of of parents/ carers/ CYP report that they feel involved and listened to (via survey). - By January 2026 75% of of parents/ carers/ CYP report that they feel involved and listened to (via survey). | On target | Owner of action agreed. Tracy and Adam met with with Ideas Alliance 15/-4/24 to agree Co-production Charter re-launch as Family Hub Conference 04/07/24 | Tracy to update Co-production Charter re new Executive Director, change to SEND Strategic Improvement Board and include Lundy Model/NHS Model.
PAP 2.3 | Coproduce the 'Tell it once' framework for children and young people with SEND with all stakeholders to identify potential options for positive change. | Rhona Hobson- Principal EP | Sept 2024 | - Revised "Tell it Once" Framework signed off by the Delivery Group. - Revised "Tell it Once" Framework communicated effectively to all partners and stakeholders through a series of engagement events and piublished on the Local Offer. | - Family Hubs have undertaken a Proof of Concept with a digital provider to implement a complete Digital Solution from 0-19 (25). - Final sign off and approval to be presented at Executive Board on 22nd February. - Final build should last 3-4 months. June 24 - Dr Hobson to create and share draft of Halton's 'Tell it once' approach. Question: How will this be presented to Stakeholders? July 24 - Dr Rhona Hobson who is leading this action point has said the policy will be drafted fully early July, now research is completed. Send to various stakeholders for ratification and feedback and then produced in final form for September on time. | - Revised "Tell it Once" approach is embedded in both culture and practice accross the Halton Partnership. - Parents and carers report that they do not have to repeatly re-tell their story to professionals. - Greater efficiency seen in CYP/ family access to services. | - Parents and carers report that they do not have to repeat their story to professionals. Greater efficiency seen in CYP/ family access to services. - By September 2024 51% of CYP/ Families surveyed, report that access to services is efficient. - By June 2025, 75% of CYP/ families surveyed report that access to services was efficient. - Reduction in request for Statutory assessment in EY/ KS1. Current % xx. Reduced to (by 2%) by December 2025 - Baseline relating to waiting times required. | On target | Dr Rhona Hobson has arranged a meeting with Charlotte Finch to discuss what needs to be done 17thApr24 - Dr Rhona Hobson is now scooping Kent LA's 'Tell it once ' approach | Dr Rhona Hobson and Charlotte Finch to meet 17thApr23 - Dr Hobson to create and share draft of Halton's 'Tell it once' approach
PAP 2.4 | Develop, consult, and sign off an information governance protocol across all health and social care partners to support the “Tell it once” culture. | Scott Middlehurst | 2024-07-01 | - Information Governance Protocol signed off by Delivery Group. Information Governance Protocol in use by all key partner agencies | - Workstream lead identified, Scott Middlehurst June 24 - Daniel Spooner/Scott Middlehurst have met with NHS colleagues about needs of this action. Daniel Spooner is arranging a SEND Digital Requirements meeting with all parties involved – awaiting of dates to be confirmed. July 24 - Daniel Spooner arranged a SEND Digital Requirements meeting with all parties involved various ways forward were showcased to all partners to consider. Time was given to partners to reflect and get back to IT managers about how to procced. Update 15.07.24- Following Synergy Web demonstration, task and finish group to be set up to agree the requirements for new case management system for SEND. This will design and implement a new system aligned to both national and local policies and timeframes. | - Services share essential information quickly and safely. - Greater efficiency seen in CYP/ Family access to services. - Needs are identified sooner and CYP benefit from earlier intervention. | - By September 2024 51% of CYP/ Families surveyed, report that access to services is efficient. - By June 2025, 75% of CYP/ families surveyed report that access to services was efficient. - Baseline relating to waiting times required. - Reduction in request for Statutory assessment in EY/ KS1. - Current % xx. Reduced to (by 2%) by December 2025 | On target | Scott Middlehurst has agreed to undertake this action and is now starting the scoping work. | Scott to report back his finding a ready for a proposal
PAP 2.5 | Complete a multi-agency joined up review of current ICT systems and processes understanding current ICT platforms used for information storing and sharing and how they interlink. | Scott Middlehurst | 2024-12-01 | - Review complete. - Review findings reported to delivery group. - ICT Systems Forward Plan produced and signed off by Delivery Group. | - Workstream lead identified June 24 - Daniel Spooner arranged a SEND Digital Requirements meeting with all parties involved various ways forward were showcased to all partners to consider. Time was given to partners to reflect and get back to IT managers about how to procced. July 24 - Following Synergy Web demonstration, task and finish group to be set up to agree the requirements for new case management system for SEND. This will design and implement a new system aligned to both national and local policies and timeframes. | - ICT systems potentially improved. - Greater efficiency seen in CYP/ Family access to services. - Needs identified sooner and CYP nenefit from earlier intervention. | - By September 2024 51% of CYP/ Families surveyed, report that access to services is efficient. - By June 2025, 75% of CYP/ families surveyed report that access to services was efficient. - Baseline relating to waiting times required. Reduction in request for Statutory assessment in EY/ KS1. - Current % xx. Reduced to (by 2%) by December 2025 | On target | After a meeting with Daniel Spooner and Scott Middlehurst it was agreed Scott wasn't the best to lead of this. | Scott Middlehurst will look for his equivalent in the NHS. Emma Power to speak to the Transformation Team to see if they are covering any of this work and if they might help
PAP 2.6 | Identification and scoping of longer term SEND IT needs utilising transformative and innovative technology solutions to drive engagement, performance, coordination and improvement across the local area system- October 2024 | Scott Middlehurst | 2024-10-01 | - Scoping Complete, findings reported to Improvement Board with recommendations for a SEND ICT Systems Forward Plan. | - Workstream lead identified June 24 - Daniel Spooner arranged a SEND Digital Requirements meeting with all parties involved various ways forward were showcased to all partners to consider. Time was given to partners to reflect and get back to IT managers about how to procced. July 24 - Following Synergy Web demonstration, task and finish group to be set up to agree the requirements for new case management system for SEND. This will design and implement a new system aligned to both national and local policies and timeframes. | - ICT systems potentially improved. - Greater efficiency seen in CYP/ Family access to services. - Needs identified sooner and CYP nenefit from earlier intervention. | - By September 2024 51% of CYP/ Families surveyed, report that access to services is efficient. - By June 2025, 75% of CYP/ families surveyed report that access to services was efficient. - Baseline relating to waiting times required. Reduction in request for Statutory assessment in EY/ KS1. - Current % xx. Reduced to (by 2%) by December 2025 | On target | Officer agreed and plan going forward agreed. Possible adding Charlotte Finch to this action | Charlotte Finch to meet with Scott to give him a brief of her requirements. Scott will then work to that
PAP 2.7 | Establish and embed Information/Data sharing protocols and systems | Sarah Brennan – Chief Operating Officer Bridgewater NHS Caroline Coyne Chief Executive Officer (CEO) Communicate Sharon English SENDIASS Adam Hindhaugh CMgr Early Help Transformation Lead Heads of Service Areas School Reps | 2024-11-01 | - Scoping and costing of "one door access" completed.Information/ Data Sharing Protocol Report signed off by Improvement Board and Published | - February 2024 - The Family Hub Programme has implemented a signed Joint Controller Agreement between the Local Authority and Bridgewater Community Healthcare Foundation Trust (ICO ref Z2436346);To ensure the best possible support is given to vulnerable children and their families. June 24 - Daniel Spooner arranged a SEND Digital Requirements meeting with all parties involved various ways forward were showcased to all partners to consider. Time was given to partners to reflect and get back to IT managers about how to procced. July 24 - Following Synergy Web demonstration, task and finish group to be set up to agree the requirements for new case management system for SEND. This will design and implement a new system aligned to both national and local policies and timeframes. | - Sevices will report information sharing is effective ensuring that children young people and their families recievve the right support at the right time and have effective robust support and/or plans in place. - Provides a comprehensive understanding of a vulnerable child's needs by integrating health and family-related information. • Promotes early identification of potential health or family-related issues, allowing for timely intervention and preventive measures that ultimately helps avoid crisis situations by addressing concerns before they escalate. • Enhances efficiency in service delivery by minimising duplication of efforts and resources and importantly reduce the burden on families by streamlining access to necessary services through a collaborative approach. • Ensures professionals have a more complete picture, enabling them to make informed and tailored decisions that better serve the child's well-being. • Reduces the risk of overlooking critical information that could impact decisions. • Enhances communication and collaboration between health and family support professionals. • Encourages a team-based approach where professionals from different domains work together for the benefit of the child. | - By September 2024 51% of CYP/ Families surveyed, report that access to services is efficient. - By June 2025, 75% of CYP/ families surveyed report that access to services was efficient. - Baseline relating to waiting times required. Reduction in request for Statutory assessment in EY/ KS1. - Current % xx. Reduced to (by 2%) by December 2025 | On target | It was suggested it might sit with Halton Transformation Unit or a team from the NHS. Due to holidays no contact made | Mike Stapleton-Chambers to speak on Sarah Brennan return from holiday - email has already been sent to request a meeting
PAP 2.8 | Implement a joined up process for an early notification tracker to be held across LA and Health that feeds into the Graduated approach. | Cathy Whyatt | 2024-09-01 | - Tracker is fully developed and implemented. - Data monitored for late identificatation | - Workstream lead identified - Cathy Whyatt Portage Worker June 24 - First meeting has been held with co-production team. Information has been collated. July 24 - A date for first subgroup session has provisionally been agreed for beginning of June with a further two sessions planned for July. The work is expected to be completed mid August when a new process will be ready to be presented to senior management. | - A robust Early Notification process, CYP with SEND will be identified earlier, have the correct support prior to starting in education. | - A robust Early Notification process, CYP with SEND will be identified earlier, have the correct support prior to starting in education. | On target | Meeting held. Stacey was unsure about this work ans was going to seek guidence from Charlotte Finch 17thApr Cathy Whyatt spoke with Sarah Campbell (EYFS Team) last week plan is to put together a subgroup from all sectors (Education/Health/Social Care/ Early help) to devise the process for Early Identification. First meeting will be by the end of the month. | Stacey Holleran to make contact with Charlotte Finch and then report back ways forward. 17thApr Sub Group meeting date to be announced and held
PAP 2.9 | Review the effectiveness of the local offer and relaunch | Tracy Ryan Policy Officer Michelle Osborne Marketing Communications Manager | 2024-06-24 | - Baseline established by measuring Footfall/ usage for the month of March 2024. - Monthly Local Offer usage reporting process agreed and published (so that footfall is reported to Improvement Group Monthly) Local Offer Engagement Plan complete and approved by Improvement Board. - Survey coproduced and published including sections on the Local Offer. Baselines established to measure improved use and approval of the Local Offer. - Results of survey shared with all stakeholders via a number of workshops and engagement sessions. - Post Survey insight report (including section on the Local Offer) submitted to Improvement Group "You said, We Did" Outcome Report (relating to Local Offer) Published. | - Local Offer Report. - Survey Questions on the Local Offer collated. June 24 - Digital solution was presented at SLT on 25th June 24 SLT didn't see it as a priority and therefore it is unlikely progress. Additional funding from elsewhere is currently being sort. One possible avenue is NHS Transformation and Partnerships All service within the Local offer as it currently stands will continue the same process to update individual pages. Communications and newsletters to users will highlight what the Local Offer is and how to use it. Adam Hindhaugh will pursue funding from additional sources. | - Inceased footfall through/ use of the Local Offer. - Children young people and families with SEND are confident in accessing all information, resources and activites displayed through the Local Offer. . | - Monthly Usage (footfall) on the Local Offer will increase by 51% from baseline by December 2025. - By June 2025 51% of CYP Family Surveyed will tell us they know what the local offer is and find it useful. - Published survey outcomes relating to Local Offer. Published post-- rvey Insight Report. Published "You said, We did" Outcome Report. | On target | Meeting held with DMT. Awaiting Zoe/SLT decision re Adam's report on linking Local Offer with Family Hubs (SEND Delivery Group action). | Progress on-hold until decision made on future of Local Offer development and review.
PAP 2.10 | Collect and collate user feedback and share “We said, we did” approach | Tracy Ryan Policy Officer Schools Rep Lindy Webb Headteacher - The Brow Adam Hindhaugh Early Help Transformation Lead | 2025-04-01 | Post Survey insight report submitted to Improvement Group. "We Said, We Did" Outcome report published allowing CYP/ Families can see how their input is shaping Service | July 24 Survey circulated, and closing date has now passed. Meetings have been held regarding analyse of survey and how the findings will be disturbed From this overtime a ‘We said – We responded’ section will be created. Workshops to be agreed to feedback findings and agree next steps Outcome report to be drafted and published Results shared with all stakeholders and published on the Local offer | CYP and their families will know how their views are influencing and shaping strategy and operational practice. CYP and their families will have incfreased confidence that their views are central to strategic design- via the publication of "We said, We did" outcome report. | Published survey outcomes. Post Survey Insight Report."We said, We did" Outcome Report. By June 2025, at least 51% of CYP and their families will tell us via survey that their input is sought, and used to guide, shape and influence strategy and operations. | On target | Action underway via CYP Survey and Parent/Carer Survey in development, awaiting agreement for survey to be issued | What feedback is available via partners? What were the outcomes, furhter discussion required on this
| Changes to interactions with parents, carers and young people are published on the Local Offer through a ‘We said – We responded’ section and there is a ‘feedback loop’ so all are aware of issues and families will have increased confidence that their views are central to strategic design- via the publication of "We said, We did" outcome report. |  | 2025-04-01 | Post Survey insight report submitted to Improvement Group. "We Said, We Did" Outcome report published allowing CYP/ Families can see how their input is shaping Service |  | CYP and their families will know how their views are influencing and shaping strategy and operational practice. CYP and their families will have incfreased confidence that their views are central to strategic design- via the publication of "We said, We did" outcome report. | Published survey outcomes. Post Survey Insight Report."We said, We did" Outcome Report. By June 2025, at least 51% of CYP and their families will tell us via survey that their input is sought, and used to guide, shape and influence strategy and operations. | On target

## Priority 3
Priority 3 - Joint Commissioning
Ref | Actions (what we will do) | Owner | Timescale | Success criteria (how we know it's achieved) | Progress (what steps we have taken so far) | Outcome/impact (the difference this made) | Evidence (how we show this) | RAG | Progress since last meeting - SSIB (SEND Strategic Improvement Board) | Next steps | Slippage with reasons
PAP 3.1 | CYP and Family Voice: Complete survey of parents/ carers/ families and CYP to appraise access to effective services (including Therapy Services), resources, assessment and settings. | C Finch/ Programme Lead | April 2024 (repeated 6 monthly) | Survey coproduced and published. Baselines established in access to effective services (including Therapy Services), resources, assessment and settings. | One survey already completed as par as part of DBV work. Expand on these to develop new survey to form baseline. SROs generating questions relative to their priority areas to help form the overall survey. Programme Lead has commenced drafting of the survey. | The partnership will possess detailed insight into the experience and views of CYP and their families on access services across the borough. Parents/CYP know they are listened to and are contributing to improvement activity | - Baseline established via first survey by June 2024, in relation to access to effective services (including Therapy Services), resources, assessment and settings. - By June 25, 20% improvement from initial baseline reported in the experience of effective services (including Therapy Services), resources, assessment and settings. - By December 2025 a further 20% improvement reported in the experience of effective services (including Therapy Services), resources, assessment and settings. - By January 2026, the wider satisfaction survey shows that 51% of CYP and their families feel services are effective across Halton. |  | Owner of action agreed. Looking at luanch to be at the Family Hub Conference in July 24 | Adam Hindhaugh to discuss with Ideas Alliance regarding the conference then meet with Tracy Ryan to finalise
PAP 3.2 | We will review, refresh and relaunch our multi-stakeholder forum that drives a strategic commissioning approach. | Kevin Greaves | 2024-06-01 | Relevant stakeholders identified to ensure multi-stakeholder attendance Refreshed membership in place with revised ToR and governance agreed. | Initial discussion has taken place with relevant stakeholders regarding the purpose and priorities of the forum to ensure alignment with wider strategic direction. There has been a meeting of the Joint Commissioning Board that has discussed the early draft of this plan and comments have been collated on both this and the task and finish group that will be formulated to deliver this work programme. | We will have improved commissioning arrangements for children and young people with SEND across Halton. We will have a strategic, joint commissioning approach to improve the sourcing and monitoring of placements and the connectivity between commissioning, the provider and all stakeholders to ensure outcomes are positive for children and young people. | - 90% attendance at forum meetings. - Parents/ carers representation in the task and finish group that will provide positive feedback following consultation. |  | Discussion taking place via task and finish group as to establishment of forum and whether to utilise existing partnership. | Initial T&F group being arranged by Claire Gurney
PAP 3.3 | We will review our Joint Commissioning resource across the LA & ICB to ensure sufficient support is available to deliver on this plan. | Philip Thomas Zoe Fearon | 2024-09-01 | There is confidence amongst stakeholders that the plan is being delivered with a visible and dedicated presence across the Halton system at a senior level. | Discussion is being planned between stakeholders to develop this initiative further. | We will have sufficient resource to drive the joint commissioning agenda with senior level representation at all key decision making fora across the Halton system. | - Baseline established via first survey by June 2024, in relation to access to effective services (including Therapy Services), resources, assessment and settings. - By June 25, 20% improvement from initial baseline reported in the experience of effective services (including Therapy Services), resources, assessment and settings. |  | Permanent Head of Commissioning Role advertised w/c 22nd April. | Commissioning Redesign Session taking place on 23rd April.
PAP 3.4 | We will review and redefine the joint commissioning strategy co-producing priorities to ensure there are robust arrangements in place to meet children and young people with SEND needs across the system | Kevin Greaves/ Philip Thomas | 2024-10-01 | Implementation of a Joint Commissioning Strategy agreed and understood by providers and families which will provide an understanding of why services have been commissioned, based on evidence. Jointly Commissioned Services will operate more effectively to meet the needs of children and young people at Halton. | The arrangements for joint commissioning have been updated to reflect changes in organisational leadership with the opportunity taken to review partners respective roles and responsibilities. | We will have improved services for children and young people with SEND across Halton. | - Baseline established via first survey by June 2024, in relation to access to effective services (including Therapy Services), resources, assessment and settings. - By June 25, 20% improvement from initial baseline reported in the experience of effective services (including Therapy Services), resources, assessment and settings. - By December 2025 a further 20% improvement reported in the experience of effective services (including Therapy Services), resources, assessment and settings. - By January 2026, the wider satisfaction survey shows that 51% of CYP and their families feel services are effective across Halton. |  | Draft in place and being reviewed | Exploring options to utilise apprentice resource
PAP 3.5 | Review and strengthen commissioning arrangements with academy, maintained and independent and alternative educational providers. | Kevin Greaves/ Charlotte Finch | 2024-12-01 | Commissioning activities will be designed to correctly address identified need to secure improved outcomes for children and young people with SEND at Halton. | Initial discussion has taken place with relevant stakeholders regarding the purpose and priorities of the forum to ensure alignment with wider strategic direction. | Increase in locally commissioned placements and provision. | Baseline established via first survey by June 2024, in relation to access to effective services (including Therapy Services), resources, assessment and settings. |  | Draft AP stratgey being developed. | Stakeholder session planned for late April
PAP 3.6 | Through an effective panel process we will identify current high cost out of borough placements and through sufficiency planning, work with local providers to provide a quality, needs led SEND service closer to home. This will ensure access to service provision that is local, responsive and timely to meeting the needs of children and young people with SEND | Kevin Greaves | 2024-12-01 | Commissioning activities will be designed to correctly address identified need to secure improved outcomes for children and young people with SEND at Halton. | Individual meetings are being planned with providers to review cases in terms of quality and cost. | Improvements in quality of placements and value for money. | - Baseline established via first survey by June 2024, in relation to access to effective services (including Therapy Services), resources, assessment and settings. - By June 25, 20% improvement from initial baseline reported in the experience of effective services (including Therapy Services), resources, assessment and settings. - By December 2025 a further 20% improvement reported in the experience of effective services (including Therapy Services), resources, assessment and settings. - By January 2026, the wider satisfaction survey shows that 51% of CYP and their families feel services are effective across Halton. |  | Current Panel process being reviewed to ensure alignment against need and to provide basis for reconfiguration. | Stakeholder session planned for late April
PAP 3.7 | We will explore options to enter into contract with a local specialist equipment provider. This provider would provide a central equipment hub that would ensure that the correct equipment can be utilised in a needs led way across the borough ensuring children can access equipment at the right time. The contract also includes maintenance, keeping equipment working for longer, ensuring the LA are working towards their Greener Future agenda. | Kevin Greaves/ Claire Gurney | 2024-07-01 | Commissioning activities will be designed to correctly address identified need to secure improved outcomes for children and young people with SEND at Halton. | Focused work has taken place with a local provider to explore possibility of commissioning a stand alone equipment service provider to provide, store, deliver and service specialist equipment. | Single storage facility in place that maintains and distributes specialist equipment that demonstrates quality and value for money. | - Average waiting time for specialist equipment to be reduced to 8 weeks by December 2024. - 100% of usable equipment remains safe and in circulation via maintenance. |  | Proposal was initially discussed at Leadership meeting, but further financial analysis was identified to support the costs of the contract and how funding could be arranged through the DSG. Meeting arranged with finance partner on 18/04/2024 for further discussion. Proposal will then be taken back to leadership for discussion. | Action 1) Meeting with finance partners to discuss contract funding- 18/04/24 Further presentation at leadership team late April.
PAP 3.8 | We will develop a Quality and performance management framework: further development of a shared SEND performance framework across education, health and social care. This will be used across a range of services to monitor the effectiveness of: - The local area in SEND identification and assessment processes; - Outcomes; - Feedback from children, young people, their families and professionals; - SEND commissioning; - Workforce plan. | Kevin Greaves/ Claire Gurney | 2025-03-31 | This information will inform and support the SEND Strategic Partnership to ensure that future services are responsive to local need at a service and system levelled will review process improvement and additional capacity across the service to exploit any further opportunities to improve working practices. | This initiative is a key element of the existing strategy addendum which is being revised in line with the strategy refresh explained in 3.3 above. This will be delivered as part of the Joint Commissioning board and monitored via the SEND Strategic Partnership Forum. | We will have improved performance monitoring of system processes across partners to allow us to accurately identify gaps and key areas of need. | - Baseline established via first survey by June 2024, in relation to access to effective services (including Therapy Services), resources, assessment and settings. - By June 25, 20% improvement from initial baseline reported in the experience of effective services (including Therapy Services), resources, assessment and settings. - By December 2025 a further 20% improvement reported in the experience of effective services (including Therapy Services), resources, assessment and settings. - By January 2026, the wider satisfaction survey shows that 51% of CYP and their families feel services are effective across Halton. |  | Information collated from existing documents to inform new model. | Draft to be produced by end of June

## Priority 4
Priority 4 - Early identification of need and access to specialist health pathways and support whilst waiting
Ref | Actions (what we will do) | Owner | Timescale | Success criteria (how we know it's achieved) | Progress (what steps we have taken so far) | Outcome/impact (the difference this made) | Evidence (how we show this) | RAG | Progress since last meeting - SSIB (SEND Strategic Improvement Board) | Next steps | Slippage with reasons
PAP 4.1 | DCO role Maternity Leave. Liaise with C&M ICB to ensure adequate cover arrangements in place. | Denise Roberts | June 2024 | - Continuity and sustainability of DCO function. - Quality assurance of health advice. - Health representation at multi-agency decision to assess panel. | 13/02/24 Discussions commenced with C&M ICB DCO | Sustainable DCO cover in C&M ICB Halton Place. | - Maintenance of 100% Quality Assured Health Advice signed off by ICB
PAP 4.2 | Needs Led Early Help Model | Karen Hampson |  | Improved, clearly defined, offer across ages and stages and continuum of need. Improved understanding of that offer/ the graduated response to meeting needs - CYP, parents / carers and professionals. Plan in place to address any identified gaps in the existing offer with clear timescales for delivery. | 23/02/24 - Initial workshop held on 21 Feb 2024 | - 'There is more join up offer across the system for key services leading to children and young people having better access to the support they need. - Reduced activity, waiting lists and waiting times in specialist health services - increased activity at universal/targeted level | - CYP and parents / carers report improved access to and experience of early help support - measure tbc - CYP and parents / carers report improvements in their needs being identified and met - measure tbc - Improved access to specialist health services (waiting times and waiting lists). See 4.3, 4.4, 4.5 and 4.6 for further details
| - Scope out existing provision including alignment with education and early help specialist provision and support whilst waiting |  | 2024-09-24 | [5 empty] | ICB Early Help have sent out survey to commissioners and partners in Sept to support with the scoping exercise 29/10/2024 - Survey of existing support against Portsmouth profiling tool underway as part of C&M-wide programme. Delay due to working at scale and challenge of agreement across multiple Places and stakeholders | Analyze survey results
| - Identify gaps in provision across ages and stages |  | 2024-10-24 | [5 empty] | 29/10/2024 - Reliant upon survey findings – analysis of findings underway locally with plans for C&M-wide review of all findings to support consistent offer across ICS footprint | To consider opportuniites where gaps are identified Await findings of survey.
| - Develop and agree improvement plan |  | 2024-11-01 | [5 empty] | Part of C&M Neurodiversity Programme
| - Implement improvement plan - adopting a graduated / Thrive approach based upon meeting need |  | 2025-01-01 | [5 empty] | Part of C&M Neurodiversity Programme
PAP 4.3 | Neurodiversity Assessment Pathway: | Karen Hampson |  | '- Pathway performance and issues affected it are clearly understood - Resourced action plan developed and agreed - Actions completed and new model implemented - Regular performance monitoring and reporting established and part of SEND oversight arrangements | - Draft performance dashboard developed - further refinement required - Pathway improvement workshop being organised to identify improvement opportunities co-produced with Halton Parent and Carers Forum | Improved access, reduced waiting lists and waiting times, improved experience for CYP and parents / carers | Neurodiversity Pathway Workshop Outcomes 'Number of children on waiting list: - Baseline - ADHD 230. Autism 848 (Feb 24) - Targets - ADHD 180 (Mar 25). Autism 700 (Mar 25) - N.B. performance likely to deteriorate before improving Time taken to complete assessment (longest waits): - Baseline ADHD 53 weeks. Autism 107 weeks (Feb 24) - Targets ADHD 40 weeks (Mar 25). Autism 78 weeks (Mar 25) - N.B. performance likely to deteriorate before improving Improved access to specialist health services (waiting times and waiting lists). See 4.4, 4.5 and 4.6 for further details - System working experience measures - tbc - Person reported experience measures - tbc
| - Review waiting list and waiting time data |  | 2024-05-01 | [5 empty] | ASD waiting times and waiting lists routinely reported. Regular reporting of ADHD waiting times and list not in place. ICB BI team working with provider to secure future reporting | Develop ADHD reporting.
| - Assess demand: historical, current and anticipated future |  | 2024-05-01 | [5 empty] | ICB BI team working with provider to secure future reporting | Develop ADHD reporting.
| - Review referral activity - quality, appropriateness and improvement opportunities - xref PAP 4.3 |  | 2024-05-01 | [5 empty] | Workshop planning underway. Awaiting delegate lists from key partner. Planning session completed 08/04/2024 29/10/2024 - Referrals declined at outset if information; questionnaires/school report et cetera not included/sufficient Developed an overarching SOP /clear pathways for the neurodevelopmental neuro disability referrals and including responses to private assessments Further work planned as part of local and C&M programmes
| - Review staffing levels and skill mix |  | 2024-10-24 | [5 empty] | 26/09/2024 - Discussions progressing with provider on opportunities to change the skill mix 29/10/2024 - SALT and Community Paediatrics key inputs to assessment pathways. See 4.4 and 4.5 for plans and progress | ICB and provider meeting w/c 21st October
| - Review system and processes for improvement opportunities |  | 2024-10-24 | [5 empty] | 29/10/2024 - Ongoing – part of C&M neurodiversity programme and provider improvement plan. | ICB and provider meeting w/c 21st October
| - Develop new delivery model, inc staff, systems and processes |  | 2024-11-24 | [5 empty] | 29/10/2024 - High level model agreed – inc early help offer using Portsmouth profiling tool. Detailed model development ongoing. Assessment process review part of C&M work with timelines dictated by that programme.
| - Implement future staffing model |  | 2024-12-01 | [5 empty] | 29/10/2024 - New model likely to mobilise during Q4 24/25 or from 1 Apr 25
| - Implement process improvements across all affected stakeholders |  | 2024-12-01 | [5 empty] | 29/10/2024 - Part of C&M work with timelines dictated by that programme.
| - Monitor improvement (waits, experience, system impacts etc) - with oversight from Halton SEND Executive Group |  | 2025-04-01
| - Introduce active waiting list management and communication |  | 2024-10-01 | [5 empty] | 29/10/2024 - Standardised reports, letters and responses introduced C&M-wide work as part of neurodiversity programme
PAP 4.4 | Speech and Language Therapy: | Lee Ellis, Clare Hunt and Karen Hampson |  | - Service performance and issues affecting it are clearly understood - Clear communications plans developed and implemented across full range of stakeholders - Any requirement to commission additional capacity (ongoing or short-term WLI) understood and actioned - Actions completed and new model implemented - Regular remedial action plan and service performance monitoring and reporting established and part of SEND oversight arrangements | - Weekly meetings between provider and commissioner in place - Remedial action plan received from provider - Capacity and demand modelling commenced - Initial further communications actions underway - Partner meetings (schools, setting, other health providers) underway to build relationships | - CYP will be able to access SALT services in a timely way - Improved partner understanding of service position - LAP will have greater visibility of issues and assurance that appropriate actions are taking place | Number of children on waiting list, waiting times (longest waits, ave wait) Improvements in performance against contract KPIs, e.g.: - response times (initial assessment (75% within 4 weeks of referral received) and treatment commenced (90% within 12 weeks)) - quality improvements (via feedback surveys) - improved appointment attendance / reduced DNAs - outcome measures reflecting the impact of speech and language therapy New provider, baselines to be established from 1st quarter performance report - System working experience measures - tbc
| - Capacity and demand > review to establish sufficiency of ongoing provision > renegotiate the contract as may be required |  | 2024-03-01 | [5 empty] | NDP demand and capacity modelled. Other areas of service provision outstanding. 29/10/2024 - No clear picture of demand, capacity or activity. Some performance data received. See separate report
| - Implement a waiting list initiative for CYP on NDP awaiting SALT assessment |  | 2024-06-01 | [5 empty] | Capacity and demand modelling undertaken. NDP assessment backlog identified and resource requirement identified . WLI SBAR agreed by ICB SLT 21 - resource and catch up trajectory. 26/09/2024 - SALT recruited by provider for WLI. Agreed SALT provider wil increase the number of assessments provided during Q3. 29/10/2024 - National shortages of SALTs affecting ability to recruit. Provider has advertised multiple times. Offer being finalised for one applicant. Another applicant withdrew. Out to advert again. | Waiting List Initiative (WLI) to commence once recruited SLT commences in post.
| - Agree and monitor service wide remedial action plan - with oversight from Halton SEND Executive Group |  | 2024-04-01 | [5 empty] | Remedial action plan in place - actively monitored and managed | Report to SEND Improvement Board
| - Implement further communications and engagement programme: > CYP and parent / carers > System partners |  | 2024-04-01 | [5 empty] | Communications / stakeholder management plan developed and implementation underway 29/10/2024 - - Moving the local offer onto a digital platform like the family hubs as part of that we are updating the speech and language pathway so it can be interactive, also looking at automated care pathways so that parents if they agree will get information along the way. We are working towards a test site for the end of the year. Communicate are taking an active role with this along with Speech and Language UK - Puling together a survey so we can gather parents and carers views on the digital pathway - HBC / C&M ICB are working with Communicate on updating communications to parents in the coming weeks. | Ongoing implementation in line with plan
| - Monitor and manage service performance and address performance variation as required - with oversight from Halton SEND Executive Group |  | Apr-Dec 24 onwards | [5 empty] | Plan in place to refine KPIs / measures and reporting schedule 29/10/2024 - Issues with quality and completeness of performance information received from provider. | Agree reporting schedule. First period reporting
| - Introduce active waiting list management and communication |  | 2024-05-01 | [5 empty] | 26/09/2024 - Agreement to support special schools and resouce bases from September. Capacity available for CYP presenting with high clinical need. 29/10/2024 - Part of communication and prioritisation process to manage capacity gap | Agree support provided to mainstream schools during Q3, Q4.
PAP 4.5 | Community paediatrics | Karen Hampson |  | - Service performance and issues affecting it are clearly understood - Resourced action plan developed and agreed - Actions completed and new model implemented - Regular performance monitoring and reporting established and part of SEND oversight arrangements N.B. significant interdependencies with 4.3 | - Draft performance dashboard developed - further refinement required - NDP pathway improvement workshop being organised to identify improvement opportunities - Business case sought from provider for advanced practitioner to change skill mix and release paediatricians to increasingly focus on specialist tasks - Provider workshop scheduled for 29 Feb 24 | Improved access, reduced waiting lists and waiting times, improved experience for CYP and parents / carers | - Number of children on waiting list. Baseline - 789 (Nov 23). Target: 600 (Mar 25) - Time taken to complete assessment: - Longest wait. Baseline - 59 weeks (Nov 23). Target: 45 (Mar 25) - % over 18 weeks. Baseline - 62.99% (Nov 23). Target: 50% (Mar 25) - Person reported experience measures - tbc
| - Conduct waiting list cleanse to reduce wasted appointment slots. |  | 2024-10-24 | [5 empty] | 29/10/2024 - Review of waiting list and caseload undertaken.
| - Education, training and awareness sessions with partners and stakeholders to support knowledge and understanding of services resulting in a reduction in inappropriate referrals. |  | 2024-11-24 | [5 empty] | 26/09/2024 - service gap analysis progressing to support this 29/10/2024 - Service improvement plan in place and being implemented Provider and ICB reviewing who can refer, referral criteria and prioritisation. Implementation to be supported by communication and training as appropriate. | Plan session once services understood
| - Review triage outcome letter to identify advice and signposting to be included. |  | 2024-10-24 | [5 empty] | 26/09/2024 - Provider reviewing all standard letters and plans in place to work with parent carer forum on this work. 29/10/2024 - Part of improvement plan Provider standardising correspondence and reports to improve communication Part of C&M programme and progress determined by timeframes in that programme | Letter reviewed with parent carer forum
| - Review transition between children's and adults’ services and, where gaps are identified, include recommendations, to be approved at Halton SEND Improvement Board, to address these. |  | 2024-10-24 | [5 empty] | 29/10/2024 - Part of improvement plan Part of C&M programme and progress determined by timeframes in that programme
| - Scope the differentiated models of assessment to enable less complex presentations to be assessed by the wider children and young people’s workforce. |  | 2024-10-01 | [5 empty] | 29/10/2024 - Part of improvement plan Activities being undertaken by wider workforce where clinically appropriate, e.g. ADHD reviews by Neurodiversity Nursing Team and GP with extended role in place. Provider and ICB reviewing who can refer, referral criteria and prioritisation. Implementation to be supported by communication and training as appropriate – likely to be Nov 24
| - Improve capacity within the service to recover long wait times. |  | 2024-09-01 | [5 empty] | 26/09/2024 - Business case received, reviewed and further impact / trajectory information requested and received. Further analysis required 29/10/2024 - Part of improvement plan Locum paediatrician and GP with extended role in place. SALT staff being recruited will support community paediatrics workload where appropriate. See SALT recruitment update in 4.4 Introduction of telephone clinics where clinically appropriate Further skill mix opportunities being considered
| - Review opportunity to introduce Patient Initiated Follow Up for service. Report to be considered by Commissioner and Provider for decision |  | 2024-10-24 | [5 empty] | 29/10/2024 - Part of improvement plan QB test aligned so is available for the first paediatric appointment, so diagnosis or non-diagnosis can be given at the first appointment.
PAP 4.6 | Other specialist health services: | Karen Hampson |  | - Service performance and issues affecting it are clearly understood - Resourced action plan developed and agreed - Actions completed and new model implemented - Regular performance monitoring and reporting established and part of SEND oversight arrangements | - Draft performance dashboard developed - further refinement required | Improved access, reduced waiting lists and waiting times, improved experience for CYP and parents / carers | - Number of children on waiting list - Waiting times (longest waits, ave wait) - Services, measures, baselines and targets tbc relevant to identified performance issues - Person reported experience measures - tbc - System working experience measures - tbc
| - Review waiting list and waiting time data |  | 2024-05-01 | [5 empty] | Commissioners regularly review this data. this will continue on an ongoing basis via contractual and provider performance meetings. Specialist health services dashboard developed
| - Identify performance issues |  | 2024-05-01 | [5 empty] | Regular reviews of performance underway and issues identified. Performance issues understood
| - Analyse causes |  | 2024-06-01 | [5 empty] | Causes understood.
| - Identify and agree solutions |  | 2024-07-01 | [5 empty] | Where are issues, these have been analysed and remedial actions agreed with providers as required
| - Implement |  | 2024-09-01 | [5 empty] | Remedial actions being implemented and progress and impact monitored
| - Monitor improvement |  | Oct 24 onwards | [5 empty] | Feeds into Board SEND dashboard via escalations as required
PAP 4.7 | Local Offer: | Tracy Ryan and Adam Hindhaugh |  | - Published information reflects the services that families should expect to receive. Auditing content provides assurance that it meets specified requirements and is up to date. - Feedback leads to developments of the site and is a measure of quality assurance |  | - There is more join up offer across the system for key services leading to children and young people having better access to the support they need. - Reduced activity, waiting lists and waiting times in specialist health services - CYP receiving the most appropriate support to meet their needs in a timely manner through a graduated, needs based model | System Working Outcomes - CYP and parents/carers report improved access to and experience of available support (PAP 2 indicators used) - Monthly Usage (footfall) on the Local Offer will increase by 51% from baseline by December 2025 - By June 2025 51% of CYP families surveyed will tell us they know what the local offer is and find it useful. - Published survey outcomes relating to the Local Offer. Plublished post survey Insight Report Published "You said, We did" Outcome Report. Improved access to specialist heatlh servcies (waiting times and waiting lists (see 4.3, 4.4, 4.5 and 4.6 for further details)
| - Undertake a refresh to incorporate changes from PAP 4.2, adopting an ages and stages x continuum of need approach to support ease of access to support across education, social care and health |  | xref Local Offer review in PAP 2 | [5 empty] | 11/09/2024 Awaiting content/information from health colleagues to publish on the Local Offer 16/09/2024 - Email sent to all Health Providers to ensure any new updates required to Local Offer are completed. Included web link https://localoffer.haltonchildrenstrust.co.uk/health/ 29/10/2024 - Information refresh ongoing.
| - Relaunch, supported by comprehensive communications plan across all stakeholders |  | xref Local Offer review in PAP 2 | [5 empty] | 11/09/2024 Co-production Sessions being held on 25 September 2024 to plan transfer of the Local Offer over to Family Hubs Online, key stakeholders invited to two sessions to progress work 16/09/2024 - Reminder sent to Merseycare, Bridgewater, Communicate CIC, Mersey & West Lancs health providers to ensure all Local Offer Information is current and updated. 25/09/2024 - Refresh of information is now connected o implementation of Beebot Digital Solution. Health Providers connected via Adam Hindhaugh. 29/10/2024 - Local Offer developing with Beebot; Weekly Project Team overseeing developments consists of Adam, Mike Stapleton Chamber, Emmalene Power and Tracy Ryan. x1 professional session undertaken to date. Migration of content from old to new ongoing as the priority, at the same time ensuring all statutory content included. Once content has been migrated start to look at the features and ongoing developments involving various teams. Health Providers networked with Lead. Beebot attending the SEND conference in November to gather user feedback. Looking at a go live date of February, maybe sooner for content.
PAP 4.8 | Develop practitioner learning and development programme (inc core and role specific mandatory training) to improve : - Awareness, understanding and identification of CYP with SEND - Awareness and understanding of specialist health services, their referral / acceptance criteria - The quality and appropriateness of referrals to services - Awareness and understanding of universal and targeted services - Support to CYP / parents / carers, including onward referral / referral to right service | Rebecca Emery | Oct 2024 | Improved offer across ages and stages and continuum of need. Improved understanding of that offer - CYP, parents / carers and professionals. Reduction in inappropriate and poor quality referrals | - Monthly ICB training model for all health practitioners, new starters or those who want a refresher, objective is to inform about SEND, DCO role and practitioner responsibility. - DCO delivering bespoke training to health providers - Multi-agency /multi-professional training to improve skill and knowledge with health services with partner agencies. | - There is more join up offer across the system for key services leading to children and young people having better access to the support they need. - better use of specialist health services, reduced activity, waiting lists and waiting times - CYP receiving the most appropriate support to meet their needs in a timely manner through a graduated, needs based model | - Training uptake rates across all relevant roles - CYP, parents / carers report improved access to and experience of early help support - Improved access to specialist health services (waiting times and waiting lists). See 4.3, 4.4, 4.5 and 4.6 for further details - Pre and post training evaluations |  | A number of 7 minute Briefings have been drafted - What is SEND? - Working with CYP with SEND - What is an Education, health and Care plan? 28/08/2024 - The DCO Training for SEND is now in implementation stage across all health providers in the C&M ICB area. It is delivered via Microsoft Teams. There are monthly dates available across the acaedemic year 2024/25 to ensure ease of access. 09/09/2024 - Training and performance half yearly report produced January - July 2024.
| Implement |  | Nov 2024 onwards | [5 empty] | 28/08/2024 - Implementation comenced August 2024. Extended invitation to LA and Education completed. 09/09/2024 - Training Information is held by central C&M ICB team broken down by Place.
PAP 4.9 | Family Hubs - optimise the opportunity they present for: | Adam Hindhaugh |  | Forward plan of actions and activities developed and implemented as part of Family Hub development programme | - Solihull Online Parenting Modules available for parents to access including 'Understanding your child with additional needs' - Meeting scheduled for March to discuss Early Years Access into Family Hubs for children with SEND - Digital Solution approved and procured - go live date scheduled for July 2024 | - Families report increased levels of confidence, knowledge and understanding through accessing parenting programmes on how to understand their child with additional needs - Families report being more supported by other parents. - Families report feeling more supported on the pathway whilst awaiting specialist information and advice | - Responses from feedback gained at the end of each parenting programme - measure and baseline tbc - Surveys and feedback gathered through the digital solution - measure and baseline tbc
| - proactive, planned and opportunistic provision of information, advice and support |  | 2025-03-01 | [5 empty] | 09/09/2024 300 parents, children & professionals attended Breast feeding celebration event. Delivered interactive session on breastfeeding to Healthy Schools Celebration Event - 100 pupils and staff attended. | - Redesign of SEND Local Offer to commence in September - Co production event planned with Woodview to look at how SEND Information, advice and support can be be better utilised using automated technology - Co production event with SEND Parent Carer Forum on 19th September to capture views on NEW SEND Local Offer - Co production event scheduled with SEND Professionals including schools on 25th September to capture views on NEW SEND Local Offer - Survey developed for CYP aged 16+ with SEND to capture views on NEW SEND Local Offer
| - integrating services / offer |  | 2025-03-01 | [5 empty] | 09/09/2024 Rrunning Welcome to the World - a 7-week evidence based ante-natal course for expectant parents from around 22 weeks of pregnancy.
| - promotion, organisation, hosting and signposting / referring to support, drop-in sessions, events and activities |  | 2025-03-01 | [5 empty] | 09/09/2024 - Halton ‘PIMH Village’ and strengthened links with all services that provide mental health support in Halton and work closely as a network. - Developed a peer support model in collaboration with our VCS colleagues, Parents in Mind, and deliver Mindful Me and Time for Me groups across the Borough. - Baby Showers are run monthly. - Strengthened the offer for dads with Fatherhood Institute and commissioned Dads Matter.
PAP 4.10 | Education Graduated Approach - communicate across stakeholders recently mapped offer, incorporating in other communications, information and education programmes as appropriate N.B. wider graduated approach elsewhere in plan - e.g. PAP4.2 | Rhona Hobson | 2024-06-01 | Specific element of the communication and education activities in 4.12 and 4.8 | Education Graduated Approach already mapped. | Increased awareness across all stakeholders of the range of education support available to meet need - including the support available to partners to the educational settings. | As evidenced in PAP 4.12 and 4.8 |  | 25/09/2024 - Graduated offer is presented on Local Offer website. All health service information is included and evidence for assurance received. Information on: - Annual Health Checks. - Woodview Childrens Development Centre (community paediatricians, physio, OT, learning disability nurses, audiology etc) - Chiild and Adolescent mental health servcies. Tell it Once Protocal developed.
PAP 4.11 | Communication Develop and implement communication and engagement activities for CYP, parents and carers and practitioners, including a range of services, where to obtain advice and support, available training and development, promotion of the Family Hubs, Healthy Child Programme, Child Development Centre, Local offer etc. PAP 2 Leading | Mike Stapleton-Chambers | Dates to align to key actions / activities in rest of PAP 4 and PAP 2 | Communication plan aligned to wider PAP 4 improvements successfully developed and delivered, with positive feedback from all relevant audiences | Communication added to PAP 2 to ensure appropriate focus across the improvement programme | Improved level of understanding of local offer, increased utilisation, more appropriate use of available services to meet need, learning and development uptake across practitioners and parents / carers. Priority four outcomes will be cross referenced and aligned with Priority 2. | As a supporting action evidence will be demonstrated through other PAP 4 actions. |  | Mike Stapleon-Chambers has set-up a briefing with schools and setting to launch the SEND Area ACtion Plan on Tuesday 430th April 2024 at DBCL Stadium. As well as schools some proffessional have also expressed and intrest in coming ot the event after hearing about is. The number booked on to date is 115 deleagates. The Family Hub has held workshops with various professional to launch their digital Hub approach to sharing information with parent/carers and professionals. 02/08/2024 - a System Communication and Engagement Group met to scope the requirments and agreement that it should be linked to One Halton Comms and Engagement Group made. This group will meet again in 6 weeks to establish progress. 09/09/2024 - Meeting on 9th October to discuss Local Area Partnership SEND Communication Strategy | Continue to enagage with stakeholders throughout the process System Comms and Engagment Group to meet 6th September 2024 SENCO Confernece 11th November 2024 - Health Providers requested to engage in market stall. 2 page 'Inside Halton' magazie to feature SEND in March 2025 - delivered to every household in Halton. Health Providers requested to contribute (PAP 2 leading)
PAP 4.12 | Increase uptake of annual health checks through: | Carl Dawood |  | - List cleanse actions undertaken by all Halton GP practices - Practices with high and low uptake identified - Examples of good practice shared from high performing practices to aide those with lower uptake (N.B. low numbers support a very targeted approach) | List cleanse completed | 75% of adults with a learning disability (aged 14 or over) who are on a GP register, will have an annual health check. | Audit of GP Registers Achieve national uptake targets (75%). 2022/23 achievement - 76.6% 2023/24 achievement - 76.6% 2024/25 achievement -
| - increase accuracy and completeness of GP registers |  | Q3 23/24
| - identify and proactively support practices with low uptake, adopting best practice form other practices. |  | Mar 24 - Mar 25 | [5 empty] | 04/09/2024 - Completed NHS England Pilot Programme to check the accuracy and completeness of all 14 GP Practice Learning Disability Registers in Halton. Identified 3 out of 14 GP practices that require support to increase uptake of Annual Health Checks. Oversight of performance is ongoing. Annual Health Check Quality Group established. | Consideration of an insert into the 'Inside Halton' Magazine underway to support practices and share good practice (see 4.11)
| - promote LD Annual Health checks to young people and families to improve registration and uptake (Part of PAP 2) |  | Jan - Mar 25 | [5 empty] | 25/09/2024 - Anyone aged 14 or over who is on their doctor's learning disability register can have a free annual health check once a year. https://www.nhs.uk/conditions/learning-disabilities/annual-health-checks/ 15/10/2024 - The Halton Medicines Management Team audited adults and children on the LD register who were prescribed psychotropics back in 2017. Re-audited in 2018 and again in 2022 (report completed). The 2022 re-audit also included patients with autism. More recently we have been part of the ICB level STOMP working group led by Carrie Barton, Head of MM in Knowsley. This group are developing principles for STOMP/STAMP reviews. We have also invited Mersey Care to come along to our Halton Medicines Optimisation Collaborative (HMOC) Meeting, which is attended by pharmacy teams from Medicines Management PCNs and practices, for an education session on STOMP/STAMP reviews. We continue to monitor for themes for improvement in STOMP/STAMP reviews are now undertaken by the ARRS funded pharmacists as per the pharmacist responsibilities in the PCN DES. | Promotion of LD Health Checks and monitoring of uptake.
PAP 4.13 | Impact Assessments Ensure a robust system and process in place to undertake Impact Assessments | CM ICB Central Team | Jun 24 | Impact assessments undertaken and considered as part of design, decision making and implementation process, with oversight from the SEND Executive Group | Psystem and process established. | 100% of services that are designed, re-designed, commissioned, de-commissioned, tendered will have a quality and equality impact assessment. | System and Process established for undertaking: - Quality Impract Assessment - Equality Impact Assessment - Digital Impact Assessment - Data Protection Impact Assessment - Health Inequality Impact Assessment
| Undertake relevant Impact Assessments to inform the work, ensuring that plans / services enable participation, including to underserved populations | Lead determined by service change. | Ongoing |  |  |  | Evidence of any impact assessments undertaken in any servie design, redesign, commissioning, de-commissioning or tendering of services. |  | 03/09/2024 - No required mpact Assessments undertaken to date

## Priority 5
Priority 5 – Education Health and Care Plans
Ref | Actions (what we will do) | Owner | Timescale | Success criteria (how we know it's achieved) | Progress (what steps we have taken so far) | Outcome/impact (the difference this made) | Evidence (how we show this) | RAG | Progress since last meeting - SSIB (SEND Strategic Improvement Board) | Next steps | Slippage with reasons
PAP 5.1 | CYP and Family Voice: Complete survey of parents/ carers/ families and CYP to appraise assessment experience and quality | C Finch/ Programme Lead | April 2024 (repeated 6 monthly) | Survey coproduced and published. Baselines established in assessment experience and quality | One survey already completed as par as part of DBV work. Expand on these to develop new survey to form baseline. SROs generating questions relative to their priority areas to help form the overall survey. | The partnership will possess detailed insight into the experience and views of CYP and their families on quality of assessment process and EHCP improved, guided by parent/carer/ CYP voice. Parents/CYP know they are listened to and are contributing to improvement activity | Baseline established via first survey by June 2024, in relation to experience of assessment and quality of new plans. By June 25, 25% improvement from initial baseline reported in the experience of assessment and quality of new plans via survey. By December 2025 a further 25% improvement reported in the experience of assessment and the quality of new plans via survey. regular monitoring in place to maintain improvements. By January 2026, the wider satisfaction survey shows that 51% of CYP and their families feel heard and effectively involved in the production of the EHCP. |  | Survey questions submitted to Emma P. Transformation liaising with Comms Team to determine best method of sharing with parents/carers and best report mechanism (and if this can feed into a dynamic dashboard) | Agree date for Survey to go live (can this be agreed at meeting on 8.04.24).
PAP 5.2 | i) Complete survey of parents/ carers/ families and CYP to appraise all elements of the SEND Area partnership relating to leadership visibility and satisfaction with general SEND Services across the Local Area Partnership | C Finch/ Programme Lead | April 2024 (repeated 6 monthly) | The partnership will possess detailed insight into the experience and views of CYP and their families on the effectiveness of Halton's leadership working and satisfaction with general SEND Services across the Local Area Partnership. Survey coproduced and published. Baselines established in understanding experiences of leadership working for improved outcomes and satisfaction with general SEND Services across the Local Area Partnership. Results of survey shared with all stakeholders via a number of workshops and engagement sessions and published on the Local Offer. Post Survey insight report submitted to Improvement Group. | survey now closed and analysis underway. | The partnership will possess detailed insight into the experience and views of CYP and their families on the effectiveness of Halton's leadership working and satisfaction with general SEND Services across the Local Area Partnership. | Parents report improved satisfaction with general SEND Services across the Local Area Partnership (Education, Health, Children's Social Care) evidenced via responses from parents/carers and children and young people to SEN satisfaction survey. by December 2024 20% improvement. June 2025 25% improvement. Dec 2025 40% improvement. KPIs across all areas of SEND show at least 25% improvement by sept 2025. (baseline measures to be agreed and established) |  | survey now closed. analysis underway. | Agree date for Survey to go live (can this be agreed at meeting on 8.04.24). comms plan to be devised and agreed. Report and PP to be drafted and shared. | delayed so further consultation could take place.
| ii) CYP and Family Voice: Complete survey of parents/ carers/ families and CYP to appraise assessment experience and quality |  | April 2024 (repeated 6 monthly) | Survey will be completed and results shared. Views of parents/ carers will be captured and feedback collated to informa plans for the future. Shared with (list stakeholders) | Programme Lead has commenced drafting of the survey. | Greater and detailed insight obtained into the experience and views of CYP and their families, in response to a comprehensive survey. Rich feedback obtained to improve practices. Quality of assessment process and EHCP improved, guided by parent/carer/ CYP voice. Parents/CYP know they are listened to and are contributing to improvement activity. | Baseline established via first survey by June 2024, in relation to experience of assessment and quality of new plans. By June 25, 25% improvement from initial baseline reported in the experience of assessment and quality of new plans via survey. By December 2025 a further 25% improvement reported in the experience of assessment and the quality of new plans via survey. regular monitoring in place to maintain improvements. By January 2026, the wider satisfaction survey shows that 51% of CYP and their famililes feel heard and effectively involved in the production of the EHCP. |  | Survey questions submitted to Emma P. Transformation liaising with Comms Team to determine best method of sharing with parents/carer and best report mechanism (and if this can feed into a dynamic dashboard) | share results with all stakeholders | as above
| iii) Develop and implement effective multi-agency and CYP, parent/carer feedback to be issued and evaluated following statutory assessment |  | 2024-06-01 | short survey sent following completion of every assessment. Feedback obtained on a regular basis and fed into improvement process to inform and influence practice | Scoping underway/ potential digital solution identified. DBV survey complete to assist in development of further survey | Feedback following each assessment improves insight into the quality of assessment and EHCP, and guides improvement activity via quality assurance process. Parents/CYP know they are listened to and are contributing to improvement activity. | by Jan 2025 50% of assessment/ new plans will be described as at least good by parents/ carers/ CYP in post assessment survey. By August 2025 65% of assessment/ new plans will be described as at least good by parents/carers/ CYP. By January 2026 90% of assessment/ new plans will be classed as at least "good" by parents/cares/ CYP. |  | Discussion with AS's team manager to determine best mechanism for sharing post assessment. | Need to establish recording and reporting mechanism. liaise with Debbie O'Connor to replicate process already in use in adults. | as above
| iv) Co-produce and implement process to review and utilise feedback to shape and improve services |  | 2024-06-01 | Feedback Process written, signed off by Board, published and in use. | no progress towards this action yet | Regular and rich feedback to improve practice. Quality of assessment process and EHCP improved, guided by parent/carer/ CYP voice. Parents/CYP know they are listened to and are contributing to improvement activity. | by Jan 2025 50% of assessment/ new plans will be described as at least good by parents/ carers/ CYP in post assessment survey. By August 2025 65% of assessment/ new plans will be described as at least good by parents/carers/ CYP. By January 2026 90% of assessment/ new plans will be classed as at least "good" by parents/cares/ CYP. |  | Discussion with AS's team manager to determine best mechanism for sharing post assessment. | Need to establish recording and reporting mechanism. liaise with Debbie O'Connor to replicate process already in use in adults. | as above
PAP 5.3 | Wider Service Review: Review the services and EHCP processes and paperwork to improve quality and timeliness of both statutory assessment and annual reviews. | C Finch | 2024-07-01 | Review completed | Review of processes undertaken | The Quality of EHCPs will be improved. Guidance on what good looks like and an will be published on the local offer. We will have understanding and agreement of what an optimum service delivery model looks like to measure against. Timeliness of assessment improved. Annual review response rates improved. | By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. by Jan 2025 50% of assessment/ new plans will be described as at least good by parents/ carers/ CYP in post assessment survey. By August 2025 65% of assessment/ new plans will be described as at least good by parents/carers/ CYP. By January 2026 90% of assessment/ new plans will be classed as at least "good" by parents/cares/ CYP. By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. By June 2025 90% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%. |  | QA processes progressing well. Envision 360 about to be launched. meeting held with principle EP, SA manager and STAs on processes around requests for assessment. and panel, to improve oversight and challenge. We want to ensure we are assessing only children who require it, to help improve efficiency. New process map in design phase. Scoping out digital solutions for EHCP assessment. Looking at existing capacity within synergy. Emma can provide verbal update on this. | Design process map for EHCP requests. Share update with schools. Update Local Offer. Benchmark exercise with other LAs re caseworker caseloads.
| Review and implement process for all EHCP outcomes to be signed off by health professionals, social care and education partners when plans are finalised. | C Finch/ S Nicholson/ K Gater/ K appleton(or DSCO) | 2024-06-24 | All plans will be signed off by each agency. A new porcess for sign off agreed and published. | Initial training completed by those signing off plans.Envision 360 purchased, and initial training completed. Further staff training scheduled. | EHCP quality will be improved, being a genuinely multi-agency assessment | By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. by Jan 2025 50% of assessment/ new plans will be described as at least good by parents/ carers/ CYP in post assessment survey. By August 2025 65% of assessment/ new plans will be described as at least good by parents/carers/ CYP. By January 2026 90% of assessment/ new plans will be classed as at least "good" by parents/cares/ CYP. By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. By June 2025 90% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%. |  | This is now happening. Action complete.
PAP 5.4 | i) Complete benchmark and analysis exercise of SEND Assessment Team to determine optimum delivery model. | E Power | 2024-05-24 | Benchmark analysis complete and optimum delivery model understood | Benchmark exercise scoped out and commenced | greater insight into the optimum model of SEND assessment delivery. Optimum team model can be designed and put in place. We will have understanding and agreement of what an optimum service delivery model looks like to measure against. Timeliness of assessment improved. Annual review response rates improved. | By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. by Jan 2025 50% of assessment/ new plans will be described as at least good by parents/ carers/ CYP in post assessment survey. By August 2025 65% of assessment/ new plans will be described as at least good by parents/carers/ CYP. By January 2026 90% of assessment/ new plans will be classed as at least "good" by parents/cares/ CYP. By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. By June 2025 90% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%. |  | Benchmark exercise partly complete. meeting taken place with BWD. difficulty obtaining information from LAs in spite of numerous attempts. data obtained fro BWD which will allows some analysis. new proposed date for completion of October 24. Ask delivery group if new date can be agreed. | Send questionaire to stat neighbours to determine caseloads. | no or limited response for other LAs
| ii) SEND Assessment Team structured reviewed and redesigned following benchmark exercise, considering options to increase capacity | C Finch | 2024-09-24 | Assessment Team Model amended for optimum delivery | Casework Stress test exercise underway | greater insight into the optimum model of SEND assessment delivery. Optimum team model can be designed and put in place. We will have understanding and agreement of what an optimum service delivery model looks like to measure against. Timeliness and quality of assessment improved. Annual review response rates improved. | By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. by Jan 2025 50% of assessment/ new plans will be described as at least good by parents/ carers/ CYP in post assessment survey. By August 2025 65% of assessment/ new plans will be described as at least good by parents/carers/ CYP. By January 2026 90% of assessment/ new plans will be classed as at least "good" by parents/cares/ CYP. By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. By June 2025 90% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%. |  | This will comence once scoping above is complete. | Design process map for EHCP requests. Share update with schools. Update Local Offer. Benchmark exercise with other LAs re caseworker caseloads. | as above
| iii) Halton LA will provide a clear plan to ensure that it has in place a permanent, suitably trained, SEN case work team of sufficient capacity to enable the effective delivery of the statutory EHC needs assessment and maintenance, including the annual review | C Finch | 2024-07-24 | benchmark analysis complete, team redesigned following benchmark. Recruitment and retention plan written and agreed. | Benchmark exercise scoped out and commenced | Timeliness and quality of EHCPs will be improved. greater insight into the optimum model of SEND assessment delivery. Optimum team model can be designed and put in place. We will have understanding and agreement of what an optimum service delivery model looks like to measure against. Timeliness of assessment improved. Annual review response rates improved. | By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. by Jan 2025 50% of assessment/ new plans will be described as at least good by parents/ carers/ CYP in post assessment survey. By August 2025 65% of assessment/ new plans will be described as at least good by parents/carers/ CYP. By January 2026 90% of assessment/ new plans will be classed as at least "good" by parents/cares/ CYP. By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. By June 2025 90% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%. |  | QA processes progressing well. Envision 360 about to be launched. meeting held with principle EP, SA manager and STAs on processes around requests for assessment. and panel, to improve oversight and challenge. We want to ensure we are assessing only children who require it, to help improve efficiency. New process map in design phase. Scoping out digital solutions for EHCP assessment. Looking at existing capacity within synergy. Emma can provide verbal update on this. This work cannot commence until scoping of processes and benchmarking is complete. It may be necessary to agree a new date of October for compleiton of this action. Delivery group to consider. | Design process map for EHCP requests. Share update with schools. Update Local Offer. Benchmark exercise with other LAs re caseworker caseloads. | as above
| iv) Training completed by all advice givers, to ensure high quality advice across services | S Nicholson | 2024-07-24 | Training completed by 100% of advice givers across all services | Training designed, method of delivery etsablished, training dates agreed | Quality and timeliness of EHCPs will be improved | By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. |  | Training has been rolled out already to schools. However, inconsistencies in subnissions indicates that further training may be required. training has been booked in so cannot be marked as complete. | Further training for all advice givers, inclusing health and social care to be designed.
| v) Development of annual review best practice model and dissemination to frontline teams. | C Finch | 2024-09-24 | Best practice model disseminated to all stakeholders. | Best practice model scoping underway. SN to lead a small task and finish group. Leaflet and step by step guide to be produced by September. Training delivered. All updates shared on loval offer and via Inclusion Group. | The quality and experience of annual reviews will be improved | By December 2025, 25% improvement reported in the experience and satisfaction of CYP and their families in relation to annual reviews-via survey. By June 2025 90% of annual reviews are completed within statutory timescales. |  | working group has now been assembled and workshops booked in to complete this action. Led by Shelley Nicholson. | Through link with DfE, identify LAs who are operating best practie re ARs. complete EHCP digitisation work.
| vi) Stakeholders ensure that EHCP annual reviews are prioritised and scrutinised from Year 9 and above. Annual reviews will inform future planning in preparation for adulthood. | H Bell/ S Nicholson. D Tierney | 2024-09-24 | Annual Reviews inform Preparation for Adulthood. The Transition team will attend year 11, 12 and 13 EHCP reviews. The transition team’s criteria accepting referrals at year 11 is agreed and published. The transition Team will attend Annual REviews from year 9 onwards for children with Significant and Complex Needs (CYP likely to require adult services).Re: EHCP YP with a diagnosed mental health disorder as their primary need with an EHCP in place, the mental health team will attend EHCP reviews from the age of 16, if referred into the service. Crisis escalation process designed, agreed and published. | The Transition team have reached out to educational settings and partners to determine people who are on EHCPs, with a view to attending reviews and being preventative and tracking our young people. Comms sent to all Secondary SChools reminding them to invite the Transition Team to Annual REviews from year 9 onwards. Training delivered by the Statutory Assessment Team manager to SENDcos, outlining how to conduct a quality annual review. Lists obtained from education settings which we screen, with a view to contribute to the meetings going forward. Meeting taken place regarding scoping for an all age disability service. The Transitions team in porcess of implementing an online referral form, to enable stakeholders to refer in timely to the team to ensure young people have the appropriate support in preparing for adulthood from year 11. | CYP with SEND are well prepared for adulthood from the earliest reasonable opportunity, benefitting from a holistic, multi agency support arrangement. . The pillars of preparing for adulthood are identified and planned for, at the earliest opportunity working in partnership with the young person, their families/carers and stake holders Transition process are significantly improved. Relationships between CYP and their families and :A support services into adulthood are significantly improved. Any arising issues are escalated and resolved quickly and effectively. | By Dec 2024, 25% improvement reported in the transition experience of CYP and theif families from y9 onwards. By June 2025, move than 50% of respondents report feeling Well prepared for adulthood. |  |  | Meet with AS manager and Háf to determine best way to progress this.
PAP 5.5 | Quality Assurance: Implement Audit tool, Envision 360, for EHCP and Annual reviews | S Nicholson | 2024-04-24 | Envision 360 will be in use. All staff will have completed the necessary training. | Envision 360 purchased, and initial training completed. Now launched and live. More auditors requested | EHCP quality will be improved | By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. by Jan 2025 50% of assessment/ new plans will be described as at least good by parents/ carers/ CYP in post assessment survey. By August 2025 65% of assessment/ new plans will be described as at least good by parents/carers/ CYP. By January 2026 90% of assessment/ new plans will be classed as at least "good" by parents/cares/ CYP. By June 2024 50% of plans will be classed as at least "good" following audit. By September 2024, 75% of plans will be classed as at least "good" following audit. By January 2025 95% of plans will be classed as a least "good" following audit. By June 2025 90% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%. |  | Almost complete. Envision training now completed. Auditors identifed. First aduit taken place. next audit to take place in September. | Implement and embed.
PAP 5.6 | Explore the benefits of the appointment of a stand-alone DSCO | Z Fearon/ K Appleton | TBC | DSCO in post | DSCO JD and Jb spec scoping complete. evaluation complete. request to advertise now completed. | All EHCPs will contain advice from Social care, following social care assessment. Advice provided by Social Care will be timely and of good quality. Social Care will play an active role and be well represented in Statutory Panels. | By June 2026 100% of requests for advice for EHCP will result in social care assessment and advice- Date to be comfirmed |  | DSCO post evaluated and permission to advertise sought. | advertise and appoint
PAP 5.7 | i) Scope out SEND portal options with a view to implementation | E Power/ C Finch | 24th March | Most effective portal identified and purchased. SEND portal Implemented. | Scoping underway/ potential digital solution identified | EHCP process efficiency improved. Timeliness of statutory assessment and Annual reviews improved. CYP and their families will enjoy an improved assessment experience. CYP and their families will feel more involved in the assessment process. | By June 2025 75% of respondents will describe their EHCP assessment experience as good. By June 2025, 75% of respondents will report feeling involved and heard during the assesment process. By June 2025 95% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%. |  | implementation/ delivery plan underway | map out process stages and timescales with assessment team
| ii) SEND portal training completed by all stakeholders | C Finch | 24th December | Training completed by 100% of advice givers across all services | Scoping underway/ potential digital solution identified | Timeliness and quality of EHCPs will be improved. | By June 2025 75% of respondents will describe their EHCP assessment experience as good. By June 2025, 75% of respondents will report feeling involved and heard during the assesment process. By June 2025 95% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%. |  | implementation delivery plan underway. training being planned | map out process stages and timescales with assessment team
| iii) SEND Portal in full use | C Finch | 25th January | Portal in full use | Scoping underway/ potential digital solution identified | Timeliness and quality of EHCPs will be improved | By June 2025 75% of respondents will describe their EHCP assessment experience as good. By June 2025, 75% of respondents will report feeling involved and heard during the assesment process. By June 2025 95% of annual reviews are completed within statutory timescales. By Jan 2025 Timeliness KPI at least 75%. By June 2025, timeliness KPI at least 85%. |  | implementation delivery plan underway. training being planned | map out process stages and timescales with assessment team